## Sheet1
Activity ID | Activity Name | Remaining Duration | Start | Finish | BL Project Start | BL Project Finish | Variance - BL Project Finish Date | Total Float | Primary Constraint
Flass Lane Early Works Programme - CL31 (Submitted) |  | 91 | 2026-04-01 | 2026-08-12 | 2026-04-01 | 2026-08-12 | 0 | -136
Key Dates (Contractual) |  | 91 | 2026-04-01 | 2026-08-12 | 2026-04-01 | 2026-08-12 | 0 | -136
AMP8-FLL-KD-1010 | Access Date | 0 | 2026-04-17 |  | 2026-04-17 |  | 0 | -111
AMP8-FLL-KD-1160 | Completion Date (Early Works Contract) | 0 |  | 01-Apr-26* |  | 2026-04-01 | 0 | -45 | Mandatory Finish
AMP8-FLL-KD-1020 | Planned Completion | 0 |  | 2026-08-11 |  | 2026-08-11 | 0 | -136
AMP8-FLL-KD-1000 | Start Date | 0 | 2026-04-01 |  | 2026-04-01 |  | 0 | -136
AMP8-FLL-KD-1030 | Terminal Float | 0 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 2026-08-12 | 0 | -136
Milestones |  | 40 | 2026-04-01 | 2026-06-01 | 2026-04-01 | 2026-06-01 | 0 | -136
AMP8-FLL-MIL-1040 | Contract Award | 0 |  | 01-Apr-26* |  | 2026-04-01 | 0 | -136 | Finish On or After
AMP8-FLL-MIL-1050 | Start date lead in/mobilisation | 10 | 2026-04-01 | 2026-04-16 | 2026-04-01 | 2026-04-16 | 0 | -136
UU Deliverables |  | 30 | 2026-04-16 | 2026-06-01 | 2026-04-16 | 2026-06-01 | 0 | -136
AMP8-FLL-UU-1680 | Client review of site layout | 5 | 2026-05-26 | 2026-06-01 | 2026-05-26 | 2026-06-01 | 0 | -136 | As Late As Possible
AMP8-FLL-UU-1500 | Client Topo & GPR receipt milestone | 0 |  | 2026-04-16 |  | 2026-04-16 | 0 | -111
AMP8-FLL-UU-1650 | S159/Third Party Access Approved | 0 |  | 2026-04-16 |  | 2026-04-16 | 0 | -111
AMP8-FLL-UU-1480 | Shaft level and location confirmation (UU) | 0 |  | 2026-04-16 |  | 2026-04-16 | 0 | -111
Procurement |  | 30 | 2026-04-17 | 2026-06-01 | 2026-04-17 | 2026-06-01 | 0 | -96
AMP8-FLL-PROC-1700 | Aggregates | 30 | 2026-04-17 | 2026-06-01 | 2026-04-17 | 2026-06-01 | 0 | -133
AMP8-FLL-PROC-1590 | Fence removal | 20 | 2026-04-17 | 2026-05-15 | 2026-04-17 | 2026-05-15 | 0 | -129
AMP8-FLL-PROC-1600 | Hoarding | 30 | 2026-04-17 | 2026-06-01 | 2026-04-17 | 2026-06-01 | 0 | -121
AMP8-FLL-PROC-1710 | HRA | 10 | 2026-04-17 | 2026-04-30 | 2026-04-17 | 2026-04-30 | 0 | -136
AMP8-FLL-PROC-1610 | Plate bearing testing | 30 | 2026-04-17 | 2026-06-01 | 2026-04-17 | 2026-06-01 | 0 | -96
AMP8-FLL-PROC-1580 | Soil & drainage | 25 | 2026-04-17 | 2026-05-22 | 2026-04-17 | 2026-05-22 | 0 | -136
AMP8-FLL-PROC-1630 | Traffic management | 30 | 2026-04-17 | 2026-06-01 | 2026-04-17 | 2026-06-01 | 0 | -136
Permits & Approvals |  | 25 | 2026-04-17 | 2026-05-22 | 2026-04-17 | 2026-05-22 | 0 | -131
Client Approvals |  | 15 | 2026-04-30 | 2026-05-22 | 2026-04-30 | 2026-05-22 | 0 | -136
AMP8-FLL-UU-1720 | HAZCON | 0 |  | 2026-04-30 |  | 2026-04-30 | 0 | -136 | As Late As Possible
AMP8-FLL-UU-1750 | HAZCON to mobilisation lead in | 15 | 2026-05-01 | 2026-05-22 | 2026-05-01 | 2026-05-22 | 0 | -136 | As Late As Possible
AMP8-FLL-UU-1730 | Shed permit granted | 0 |  | 2026-05-22 |  | 2026-05-22 | 0 | -136 | As Late As Possible
Streetworks & Traffic Management |  | 25 | 2026-04-17 | 2026-05-22 | 2026-04-17 | 2026-05-22 | 0 | -131
AMP8-FLL-ECI-1360 | Consultation with Compliance Officer | 0 |  | 2026-05-22 |  | 2026-05-22 | 0 | -131
AMP8-FLL-ECI-1640 | Produce and submit Streetworks permit (PAA) | 25 | 2026-04-17 | 2026-05-22 | 2026-04-17 | 2026-05-22 | 0 | -131
AMP8-FLL-ECI-1340 | TTRO Application, Submission and Review period | 25 | 2026-04-17 | 2026-05-22 | 2026-04-17 | 2026-05-22 | 0 | -131
AMP8-FLL-ECI-1660 | TTRO traffic management approval | 0 |  | 2026-05-22 |  | 2026-05-22 | 0 | -131
HRA |  | 15 | 2026-05-01 | 2026-05-22 | 2026-05-01 | 2026-05-22 | 0 | -136
AMP8-FLL-ECI-1690 | HRA screening review period (UU) | 5 | 2026-05-18 | 2026-05-22 | 2026-05-18 | 2026-05-22 | 0 | -136
AMP8-FLL-ECI-1670 | Produce HRA screening report | 10 | 2026-05-01 | 2026-05-15 | 2026-05-01 | 2026-05-15 | 0 | -136
AMP8-FLL-ECI-1680 | Submit HRA screening report | 0 |  | 2026-05-15 |  | 2026-05-15 | 0 | -136
Early Works |  | 81 | 2026-04-16 | 2026-08-11 | 2026-04-16 | 2026-08-11 | 0 | -136
Temp Works Design |  | 24 | 2026-04-16 | 2026-05-21 | 2026-04-16 | 2026-05-21 | 0 | -115
AMP8-FLL-DED-1550 | Hoarding TWD completion milestone | 0 |  | 2026-05-21 |  | 2026-05-21 | 0 | -115
AMP8-FLL-DED-1140 | MAE contract award | 0 |  | 2026-04-16 |  | 2026-04-16 | 0 | -130
AMP8-FLL-DED-1130 | MAE design period | 20 | 2026-04-17 | 2026-05-15 | 2026-04-17 | 2026-05-15 | 0 | -130
AMP8-FLL-DED-1120 | MAE mobilisation | 0 |  | 2026-04-16 |  | 2026-04-16 | 0 | -130
AMP8-FLL-DED-1150 | TRA - Time Risk Allowance (20%) | 4 | 2026-05-18 | 2026-05-21 | 2026-05-18 | 2026-05-21 | 0 | -130
AMP8-FLL-DED-1570 | Working platform TWD completion milestones | 0 |  | 2026-05-21 |  | 2026-05-21 | 0 | -127
Enabling Activities Sitewide |  | 56 | 2026-05-26 | 2026-08-11 | 2026-05-26 | 2026-08-11 | 0 | -136
Duration |  | 54 | 2026-05-28 | 2026-08-11 | 2026-05-28 | 2026-08-11 | 0 | -136
AMP8-FLL-EAW-1430 | Construction duration (LOE) | 54 | 2026-05-28 | 2026-08-11 | 2026-05-28 | 2026-08-11 | 0 | -136
Construction |  | 56 | 2026-05-26 | 2026-08-11 | 2026-05-26 | 2026-08-11 | 0 | -136
AMP8-FLL-EAW-1250 | Aggregates and install piling platform | 5 | 2026-07-21 | 2026-07-27 | 2026-07-21 | 2026-07-27 | 0 | -136
AMP8-FLL-EAW-1220 | Cut and Fill to Level Compound | 5 | 2026-06-30 | 2026-07-06 | 2026-06-30 | 2026-07-06 | 0 | -136
AMP8-FLL-EAW-1270 | De-mobilisation | 1 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 0 | -136
AMP8-FLL-EAW-1350 | Enabling works TRA - Time Risk Allowance (30% Overall) | 9 | 2026-07-30 | 2026-08-11 | 2026-07-30 | 2026-08-11 | 0 | -136
AMP8-FLL-EAW-1240 | Import aggregates and construct compound | 15 | 2026-07-07 | 2026-07-27 | 2026-07-07 | 2026-07-27 | 0 | -136
AMP8-FLL-EAW-1180 | Install Cut-off drainage to working area boundary (Connection to Ext Network) | 7 | 2026-06-12 | 2026-06-22 | 2026-06-12 | 2026-06-22 | 0 | -136
AMP8-FLL-EAW-1110 | Mobilise to main compound | 1 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 0 | -136
AMP8-FLL-EAW-1260 | Plate Bearing Tests | 2 | 2026-07-28 | 2026-07-29 | 2026-07-28 | 2026-07-29 | 0 | -136
AMP8-FLL-EAW-1170 | Pre-entry soil and Drainage survey (Main compound) | 5 | 2026-05-26 | 2026-06-01 | 2026-05-26 | 2026-06-01 | 0 | -136
AMP8-FLL-EAW-1410 | Remove Ext fence and install access gate to field | 3 | 2026-05-28 | 2026-06-01 | 2026-05-28 | 2026-06-01 | 0 | -136
AMP8-FLL-EAW-1190 | Set up Temporary fencing | 2 | 2026-06-03 | 2026-06-04 | 2026-06-03 | 2026-06-04 | 0 | -136
AMP8-FLL-EAW-1200 | Site Hoarding | 20 | 2026-06-23 | 2026-07-20 | 2026-06-23 | 2026-07-20 | 0 | -136
AMP8-FLL-EAW-1420 | Soil strip and import aggregates for Initial Compound area | 5 | 2026-06-05 | 2026-06-11 | 2026-06-05 | 2026-06-11 | 0 | -136
AMP8-FLL-EAW-1210 | Topsoil Strip and stockpile | 5 | 2026-06-23 | 2026-06-29 | 2026-06-23 | 2026-06-29 | 0 | -136
Completion |  | 0 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 2026-08-11 | 0 | -136
AMP8-FLL-EAW-1440 | Client acceptance - Construction manager sign off | 0 |  | 2026-08-11 |  | 2026-08-11 | 0 | -136