## Sheet1
Activity ID | Activity Name | Start | Finish | BL1 Start | BL1 Finish | Variance - BL1 Finish Date | Total Float | Remaining Duration | Activity % Complete | Comments
FER-CD-1000 | Contract Start Date | 2026-02-16 |  | 2026-02-16 |  | 0 |  | 0 | 100
FER-CD-1020 | Terminal Float | 2026-09-25 | 2026-10-07 | 2026-09-02 | 2026-09-14 | -17 | -17 | 9 | 0
FER-CD-1010 | Contract Completion |  | 2026-10-07 |  | 2026-09-14 | -17 | -17 | 0 | 0
FER-PD-1000 | Submission of shaft concept design to MGE |  | 2026-06-12 |  | 2026-05-19 | -17 | 56 | 0 | 0
FER-PD-1010 | Submission of Outline Design Scope Freeze |  | 2026-06-29 |  | 2026-06-04 | -17 | 46 | 0 | 0
FER-PD-1020 | Submission of Full Outline Design Package |  | 2026-09-24 |  | 2026-09-01 | -17 | -17 | 0 | 0
FER-PD-1030 | Planned Project Completion |  | 2026-09-24 |  | 2026-09-01 | -17 | -17 | 0 | 0
FER-CHA-1010 | JMS-MAE-PS-EWN-000005 - Naming Conventions and Protocols | 2026-04-10 |  | 2026-04-10 |  | 0 |  | 0 | 100
FER-CHA-1020 | JMS001-PS-RFQ-000001 - Optioneering Assessment | 2026-05-11 | [5 empty] | 0 | 100
FER-DEP-1000 | [GET] - Topographical data from UU | 2026-02-16 |  | 2026-02-16 |  | 0 |  | 0 | 100
FER-DEP-1010 | [GET] - All GI data and reports | 2026-02-16 |  | 2026-02-16 |  | 0 |  | 0 | 100
FER-DEP-1020 | [GET] - Confirmation whether shaft lining is required | 2026-03-12 |  | 2026-03-12 |  | 0 |  | 0 | 100
FER-DEP-1040 | [GET] - Maximum flowrate in overflow pipe | 2026-03-13 |  | 2026-03-13 |  | 0 |  | 0 | 100
FER-DEP-1050 | [GET] - Maximum water level in existing Ferry PS | 2026-03-13 |  | 2026-03-13 |  | 0 |  | 0 | 100
FER-DEP-1070 | [GET] - Manhole records/cards | 2026-03-20 |  | 2026-03-20 |  | 0 |  | 0 | 100
FER-DEP-1080 | [GET] - Confirm preferred pipe material for connection between new MHs and shaft | 2026-03-20 |  | 2026-03-20 |  | 0 |  | 0 | 100
FER-DEP-1090 | [GET] - Confirmation on how Murphy intends to form pipe entry/exits & how intend to install pipework | 2026-03-20 |  | 2026-03-20 |  | 0 |  | 0 | 100
FER-DEP-1100 | [GET] - Confirm detail to be used at cover slab/top of pile interface | 2026-03-20 |  | 2026-03-20 |  | 0 |  | 0 | 100
FER-DEP-1110 | [GET] - Agree shaft design concept with UU | 2026-03-20 |  | 2026-03-20 |  | 0 |  | 0 | 100
FER-DEP-1120 | [GET] - All existing drawings in dwg format | 2026-03-20 |  | 2026-03-20 |  | 0 |  | 0 | 100
FER-DEP-1130 | [GET] - Catchment Area EPD (Explosion Protection Document)- Confirmation of Hazardous Substances in existing tank | 2026-06-01 |  | 2026-05-01 |  | -19 | 36 | 0 | 0
FER-MOB-1000 | Mobilisation | 2026-02-16 | 2026-02-20 | 2026-02-16 | 2026-02-20 | 0 |  | 0 | 100
FER-MOB-1010 | Review Information and raise RFI/TQs | 2026-02-23 | 2026-02-27 | 2026-02-23 | 2026-02-27 | 0 |  | 0 | 100
FER-MOB-1020 | Meeting with Murphy & UU - Confirmation of revised scope received | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 0 |  | 0 | 100
FER-MOB-1030 | Review Information and raise RFI/TQs based on new scope of works | 2026-03-09 | 2026-03-13 | 2026-03-09 | 2026-03-13 | 0 |  | 0 | 100
FER-MOB-1040 | Murphy Response to TQs | 2026-03-16 | 2026-03-27 | 2026-03-16 | 2026-03-27 | 0 |  | 0 | 100
FER-CHA-1030 | Outfall pipework optioneering | 2026-04-29 | 2026-05-13 |  |  |  |  | 0 | 100
FER-3D-1020 | Model Existing Tank | 2026-03-30 | 2026-04-23 | 2026-03-30 | 2026-04-23 | 0 |  | 0 | 100
FER-3D-1030 | Build Terrain Model | 2026-03-30 | 2026-04-23 | 2026-03-30 | 2026-04-23 | 0 |  | 0 | 100
FER-3D-1000 | BIM Set Up | 2026-04-10 | 2026-04-23 | 2026-04-10 | 2026-04-23 | 0 |  | 0 | 100
FER-3D-1040 | Civil Modelling - Tank | 2026-04-24 | 2026-04-30 | 2026-04-24 | 2026-04-30 | 0 |  | 0 | 100
FER-3D-1060 | Civil Modelling - Other Assets | 2026-05-01 | 2026-06-05 | 2026-05-01 | 2026-05-22 | -9 | -17 | 5 | 66.67
FER-3D-1070 | Mechanical Modelling | 2026-05-01 | 2026-06-05 | 2026-05-01 | 2026-05-22 | -9 | -17 | 5 | 66.67
FER-3D-1050 | Network modelling (to be done by Arup) | 2026-05-21 |  | 2026-05-01 |  | -13 |  | 0 | 100 | 5 Day lag added from when optioneering is complete to allow ARUP to complete modelling
FER-3D-1010 | BIM Execution Plan | 2026-06-01 | 2026-06-12 | 2026-05-01 | 2026-05-15 | -19 | -7 | 10 | 0
FER-CSD-1000 | Determine entry/exit levels for pipework to and from overflow pipe | 2026-03-30 | 2026-04-02 | 2026-03-30 | 2026-04-02 | 0 |  | 0 | 100
FER-CSD-1010 | Review GI and determine preferred pile toe-in depth | 2026-03-30 | 2026-04-02 | 2026-03-30 | 2026-04-02 | 0 |  | 0 | 100
FER-CSD-1020 | Estimate conservative thickness for structural slab and steel density | 2026-03-30 | 2026-04-02 | 2026-03-30 | 2026-04-02 | 0 |  | 0 | 100
FER-CSD-1030 | Assessment to determine internal sizing of shaft | 2026-03-30 | 2026-04-02 | 2026-03-30 | 2026-04-02 | 0 |  | 0 | 100
FER-CSD-1040 | [GET] - MGE to provide initial guidance on pile size and spacing |  | 2026-06-01 |  | 2026-05-05 | -17 | -17 | 0 | 0 | 5 Day lag from when Network modelling completed
FER-CSD-1050 | Check on shaft sizing and buoyancy assessment | 2026-06-01 | 2026-06-05 | 2026-05-06 | 2026-05-12 | -17 | -17 | 5 | 0
FER-CSD-1060 | Produce 2D conept drawing | 2026-06-08 | 2026-06-12 | 2026-05-13 | 2026-05-19 | -17 | -17 | 5 | 0
FER-CSD-1070 | MGE Detailed Pile Design | 2026-06-15 | 2026-06-26 | 2026-05-20 | 2026-06-03 | -17 | -12 | 10 | 0
FER-CSD-1080 | CAT2 check on MGE pile design | 2026-06-29 | 2026-07-03 | 2026-06-04 | 2026-06-10 | -17 | -12 | 5 | 0
FER-CIV-1000 | Manhole Schedule | 2026-03-30 | 2026-04-02 | 2026-03-30 | 2026-04-02 | 0 |  | 0 | 100
FER-CIV-1010 | Outline drawing for connection into existing manhole on inlet pipe | 2026-04-07 | 2026-04-13 | 2026-04-07 | 2026-04-13 | 0 |  | 0 | 100
FER-CIV-1020 | GA & Long sections of pipe entry/exit pipework from new MHs | 2026-04-14 | 2026-04-20 | 2026-04-14 | 2026-04-20 | 0 |  | 0 | 100
FER-CIV-1030 | Valve chamber standard detail drawing showing dimensions and layout | 2026-04-21 | 2026-05-22 | 2026-04-21 | 2026-05-08 | -10 |  | 0 | 100
FER-CIV-1040 | Kiosk slab proposal | 2026-05-26 | 2026-06-01 | 2026-05-11 | 2026-05-15 | -10 | 2 | 1 | 80
FER-CIV-1050 | Shaft penetrations & details drawing | 2026-06-15 | 2026-06-26 | 2026-05-20 | 2026-06-03 | -17 | -17 | 10 | 0
FER-MEC-1000 | Line sizing | 2026-03-30 | 2026-04-10 | 2026-03-30 | 2026-04-10 | 0 |  | 0 | 100
FER-MEC-1010 | Mechanical calculations - head loss calcs | 2026-04-13 | 2026-04-24 | 2026-04-13 | 2026-04-24 | 0 |  | 0 | 100
FER-MEC-1020 | Pump system curve and calcs with pump selection | 2026-04-27 | 2026-05-22 | 2026-04-27 | 2026-05-11 | -9 |  | 0 | 100
FER-MEC-1120 | MAE Raised JMS-MAE-TQ-000044 | 2026-04-30 | [5 empty] | 0 | 100
FER-MEC-1130 | [GET] response to JMS-MAE-TQ-000044 |  | 2026-05-12 |  |  |  |  | 0 | 100
FER-PRO-1010 | Basis of Design | 2026-03-23 | 2026-04-17 | 2026-03-23 | 2026-04-17 | 0 |  | 0 | 100
FER-PRO-1000 | Outline P&IDs | 2026-03-30 | 2026-04-17 | 2026-03-30 | 2026-04-17 | 0 |  | 0 | 100
FER-PRO-1020 | Control Philosophy | 2026-04-20 | 2026-04-24 | 2026-04-20 | 2026-04-24 | 0 |  | 0 | 100
FER-REV-1000 | Submission of Outline Design Pack | 2026-06-29 |  | 2026-06-04 |  | -17 | -17 | 0 | 0
FER-REV-1010 | Client Review of Design Pack | 2026-06-29 | 2026-07-10 | 2026-06-04 | 2026-06-17 | -17 | -17 | 10 | 0
FER-GEO-1000 | Review available GI for shaft design | 2026-03-16 | 2026-03-20 | 2026-03-16 | 2026-03-20 | 0 |  | 0 | 100
FER-GEO-1010 | GDR | 2026-06-15 | 2026-06-19 | 2026-05-20 | 2026-05-27 | -17 | 21 | 5 | 0
FER-GEO-1020 | Client Review of GDR | 2026-06-22 | 2026-07-03 | 2026-05-28 | 2026-06-10 | -17 | 21 | 10 | 0
FER-CIV-1060 | Benching design | 2026-07-13 | 2026-07-24 | 2026-06-18 | 2026-07-01 | -17 | -17 | 10 | 0
FER-CIV-1070 | Cover slab design | 2026-07-27 | 2026-07-31 | 2026-07-02 | 2026-07-08 | -17 | -17 | 5 | 0
FER-CIV-1080 | Pipe entry/exit from MHs | 2026-08-03 | 2026-08-14 | 2026-07-09 | 2026-07-22 | -17 | -17 | 10 | 0
FER-CIV-1090 | Pipe exit details for rising mains | 2026-08-17 | 2026-08-21 | 2026-07-23 | 2026-07-29 | -17 | -17 | 5 | 0
FER-CIV-1100 | MH01 & MH02 Design | 2026-07-13 | 2026-07-21 | 2026-06-18 | 2026-06-26 | -17 | -16 | 7 | 0
FER-CIV-1110 | Pipework from MHs to Shaft | 2026-07-22 | 2026-07-28 | 2026-06-29 | 2026-07-03 | -17 | -16 | 5 | 0
FER-CIV-1120 | Pipe entry/exit details | 2026-07-29 | 2026-08-04 | 2026-07-06 | 2026-07-10 | -17 | -16 | 5 | 0
FER-CIV-1130 | Valve Chamber | 2026-08-05 | 2026-08-11 | 2026-07-13 | 2026-07-17 | -17 | -16 | 5 | 0
FER-CIV-1140 | Flowmeter Chamber | 2026-08-12 | 2026-08-18 | 2026-07-20 | 2026-07-24 | -17 | -16 | 5 | 0
FER-CIV-1150 | Civils Pipe Design | 2026-08-19 | 2026-08-25 | 2026-07-27 | 2026-07-31 | -17 | -16 | 5 | 0
FER-CIV-1160 | Tank kiosk enclosure foundation | 2026-07-13 | 2026-07-17 | 2026-06-18 | 2026-06-24 | -17 | 11 | 5 | 0
FER-CIV-1170 | Assessment of exit details | 2026-08-24 | 2026-08-26 | 2026-07-30 | 2026-08-03 | -17 | -17 | 3 | 0
FER-CIV-1180 | Routing & Design | 2026-08-03 | 2026-08-07 | 2026-07-09 | 2026-07-15 | -17 | -4 | 5 | 0
FER-PRO-1030 | HAZOP & ALM Workshop | 2026-06-01 | 2026-06-01 | 2026-05-12 | 2026-05-12 | -12 | 38 | 0 | 0
FER-PRO-1040 | HAZOP & ALM action and close out | 2026-06-01 | 2026-06-10 | 2026-05-13 | 2026-05-27 | -10 | 38 | 8 | 0
FER-MEC-1030 | DSEAR Assessment | 2026-07-13 | 2026-07-24 | 2026-06-18 | 2026-07-01 | -17 | 6 | 10 | 0
FER-MEC-1040 | Significant Site Hazard Identification Plan | 2026-08-03 | 2026-08-07 | 2026-07-09 | 2026-07-15 | -17 | -4 | 5 | 0
FER-MEC-1050 | Material Take Off | 2026-08-03 | 2026-08-07 | 2026-07-09 | 2026-07-15 | -17 | -4 | 5 | 0
FER-MEC-1060 | GA Drawing - Pumps in shaft GA & Risers | 2026-07-13 | 2026-07-15 | 2026-06-18 | 2026-06-22 | -17 | -11 | 3 | 0
FER-MEC-1070 | GA Drawing - Tank Entry Pipe | 2026-07-16 | 2026-07-20 | 2026-06-23 | 2026-06-25 | -17 | -11 | 3 | 0
FER-MEC-1080 | GA Drawing - Tremie Pipe | 2026-07-21 | 2026-07-23 | 2026-06-26 | 2026-06-30 | -17 | -11 | 3 | 0
FER-MEC-1090 | GA Drawing - Fluidic Mixer | 2026-07-24 | 2026-07-28 | 2026-07-01 | 2026-07-03 | -17 | -11 | 3 | 0
FER-MEC-1110 | Plan and long section for rising main | 2026-07-29 | 2026-08-11 | 2026-07-06 | 2026-07-17 | -17 | -11 | 10 | 0
FER-MEC-1100 | Pipework layout plan c/w pipework and manhole schedule | 2026-07-29 | 2026-07-31 | 2026-07-06 | 2026-07-08 | -17 | -4 | 3 | 0
FER-EICA-1100 | Site Visit | 2026-05-14 | [5 empty] | 0 | 100
FER-EICA-1000 | User Requirement Specification | 2026-05-18 | 2026-05-26 | 2026-04-27 | 2026-05-11 | -10 |  | 0 | 100
FER-EICA-1020 | Load Schedule | 2026-05-26 | 2026-05-28 | 2026-05-12 | 2026-05-14 | -9 |  | 0 | 100
FER-EICA-1010 | Network Architecture Drawing | 2026-05-27 | 2026-06-02 | 2026-05-12 | 2026-05-18 | -10 | 31 | 2 | 60
FER-EICA-1040 | Power Supply Assessment | 2026-05-29 | 2026-06-11 | 2026-05-15 | 2026-05-29 | -9 | 22 | 9 | 10
FER-EICA-1030 | Telemetry Schedules | 2026-06-03 | 2026-06-05 | 2026-05-19 | 2026-05-21 | -10 | 31 | 3 | 0
FER-EICA-1050 | Lighting Protection Risk Assessment | 2026-06-12 | 2026-06-25 | 2026-06-01 | 2026-06-12 | -9 | 22 | 10 | 0
FER-EICA-1060 | Instrument Schedule | 2026-06-26 | 2026-07-02 | 2026-06-15 | 2026-06-19 | -9 | 22 | 5 | 0
FER-EICA-1070 | Single Line Diagrams | 2026-05-29 | 2026-06-04 | 2026-05-15 | 2026-05-21 | -9 | 32 | 4 | 20
FER-EICA-1080 | Block Cable Diagrams | 2026-06-08 | 2026-06-12 | 2026-05-22 | 2026-05-29 | -10 | 31 | 5 | 0
FER-EICA-1090 | DNO/MCC Main Incomer Kiosk Location Plan | 2026-06-15 | 2026-06-19 | 2026-06-01 | 2026-06-05 | -10 | 31 | 5 | 0
FER-REV-1020 | Submission of Outline Design Pack | 2026-08-27 |  | 2026-08-04 |  | -17 | -17 | 0 | 0
FER-REV-1030 | Client Review of Design Pack | 2026-08-27 | 2026-09-10 | 2026-08-04 | 2026-08-17 | -17 | -17 | 10 | 0
FER-REV-1040 | Review and update drawings | 2026-09-11 | 2026-09-24 | 2026-08-18 | 2026-09-01 | -17 | -17 | 10 | 0
FER-REV-1050 | Final Submission |  | 2026-09-24 |  | 2026-09-01 | -17 | -17 | 0 | 0
FER-DEP-1030 | [GET] - Historical model | 2026-03-13 |  | 2026-03-13 |  | 0 |  | 0 | 100
FER-DEP-1060 | [GET] - Historical asbuilt drawings | 2026-03-20 |  | 2026-03-20 |  | 0 |  | 0 | 100