## Sheet1
Activity ID | Activity Name | Start | Finish | Remaining Duration | Total Float | Calendar
AMP8-DD&B-ROS-MIL-1000 | Contract Award | 2025-11-24 |  | 0.00d | 0.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-MIL-1010 | Start Construction | 2026-01-26 |  | 0.00d | 19.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-MIL-1060 | Start Early works | 2026-01-26 |  | 0.00d | 0.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2040 | Produce 168 Drawings and Issue to UU | 2026-01-05 | 2026-01-15 | 11.00d | 0.00d | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-2050 | UU Serve Notice to Landowner |  | 2026-01-19 | 0.00d | 0.00d | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-2060 | Section 168 - Power to Access to Carry Out Surveys Shaft 5,6 & 7 - Rossall School | 2026-01-20 | 2026-01-26 | 7.00d | 0.00d | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-2160 | Produce 159 Drawings and Issue to UU | 14-Jan-26* | 2026-01-21 | 6.00d | 1.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2170 | UU Serve Notice to Landowner | 2026-01-21 | 2026-01-21 | 1.00d | 78.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2510 | Land Owner Agrees Early Entry | 2026-01-21 |  | 0.00d | 49.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2190 | Produce 159 Drawings and Issue to UU | 13-Jan-26* | 2026-01-21 | 7.00d | 45.00d | ENT 5 Day Working
AMP8-DD&B-ROS-ECI-2200 | UU Serve Notice to Landowner | 2026-01-22 | 2026-02-03 | 13.00d | 103.00d | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-2230 | UU Serve Notice to Landowner | 2026-01-22 | 2026-01-27 | 4.00d | 45.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2240 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 2026-01-20 | 5.00d | 65.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2250 | UU Serve Notice to Landowner | 2026-01-21 | 2026-01-27 | 5.00d | 65.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2270 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 2026-01-20 | 5.00d | 65.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2280 | UU Serve Notice to Landowner | 2026-01-21 | 2026-02-02 | 9.00d | 74.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2300 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 2026-01-21 | 6.00d | 65.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2310 | UU Serve Notice to Landowner | 2026-01-22 | 2026-01-26 | 3.00d | 66.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2330 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 2026-01-21 | 6.00d | 65.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2340 | UU Serve Notice to Landowner | 2026-01-22 | 2026-01-27 | 4.00d | 65.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1570 | WYRE BOROUGH COUNCIL - King Georges Playing Fields - RL Boundary, no boreholes | 2026-01-14 | 2026-01-23 | 8.00d | 1.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2360 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 2026-01-20 | 5.00d | 4.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2370 | UU Serve Notice to Landowner | 2026-01-21 | 2026-01-27 | 5.00d | 47.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2500 | Land Owner Agrees Early Entry | 2026-01-21 |  | 0.00d | 37.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2390 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 2026-01-20 | 5.00d | 4.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2400 | UU Serve Notice to Landowner | 2026-01-21 | 2026-01-27 | 5.00d | 47.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2520 | Land Owner Agrees Early Entry | 2026-01-21 |  | 0.00d | 52.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2450 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 2026-01-20 | 5.00d | 4.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2460 | UU Serve Notice to Landowner | 2026-01-21 | 2026-01-27 | 5.00d | 47.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2480 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 2026-01-20 | 5.00d | 4.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2490 | UU Serve Notice to Landowner | 2026-01-21 | 2026-01-27 | 5.00d | 47.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2540 | Access Protection Survey Required | 2026-01-28 | 2026-02-03 | 5.00d | 104.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2420 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 2026-01-20 | 5.00d | 4.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2430 | UU Serve Notice to Landowner | 2026-01-21 | 2026-01-29 | 7.00d | 82.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2530 | Land Owner Agrees Early Entry | 2026-01-21 |  | 0.00d | 4.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2590 | UU Prepare and Issue Section 61 | 2026-01-19 | 2026-01-23 | 5.00d | 22.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2620 | Section 61- Approval - Shaft 1 | 2026-01-24 |  | 0.00d | 119.00d | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-2630 | UU Prepare and Issue Section 61 | 2026-01-19 | 2026-01-23 | 5.00d | 22.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2650 | Section 61- Approval - Shaft 2 | 2026-01-24 |  | 0.00d | 117.00d | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-2660 | UU Prepare and Issue Section 61 | 2026-01-19 | 2026-01-23 | 5.00d | 22.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2680 | Section 61- Approval - Shaft 3 | 2026-01-24 |  | 0.00d | 159.00d | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-2690 | UU Prepare and Issue Section 61 | 2026-01-19 | 2026-01-23 | 5.00d | 22.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2710 | Section 61- Approval - Shaft 4 | 2026-01-24 |  | 0.00d | 73.00d | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-2720 | UU Prepare and Issue Section 61 | 2026-01-19 | 2026-01-23 | 5.00d | 22.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2740 | Section 61- Approval - Shaft 5 | 2026-01-24 |  | 0.00d | 34.00d | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-2750 | UU Prepare and Issue Section 61 | 2026-01-19 | 2026-01-23 | 5.00d | 22.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2770 | Section 61- Approval - Shaft 7 | 2026-01-24 |  | 0.00d | 32.00d | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-1390 | Ground Investigation - Shaft 7 West Way - 2 Boreholes 5 Feb | 2026-01-26 | 2026-02-19 | 19.00d | 6.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1370 | Ground Investigation Shaft 5 - West Way - 2 Boreholes 5 Feb | 2026-01-28 | 2026-02-20 | 18.00d | 6.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1470 | Delay - Landfill site issue - EWN 18 | 2026-02-04 | 2026-02-27 | 18.00d | 24.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1350 | Ground Investigation Shaft 3 - Cardinal Allen High School - 2 Boreholes | 2026-03-02 | 2026-03-06 | 5.00d | 24.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1410 | Ground Investigation Report | 2026-03-09 | 2026-03-20 | 10.00d | 24.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1440 | Delay - Landfill site Issue - EWN18 | 16-Feb-26* | 2026-02-27 | 10.00d | 24.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1340 | Ground Investigation Shaft 2 - Broadwater Woods - 2 Boreholes | 2026-03-02 | 2026-03-06 | 5.00d | 24.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1400 | Ground Investigation Report | 2026-03-09 | 2026-03-20 | 10.00d | 24.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1200 | Delay - Landfill site issue - EWN 18 | 2026-02-16 | 2026-02-27 | 10.00d | 24.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1170 | Ground Investigation Shaft 1 - Fleetwood Works- 2 no Boreholes | 2026-03-02 | 2026-03-06 | 5.00d | 24.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1180 | Ground Investigation Report | 2026-03-09 | 2026-03-20 | 10.00d | 24.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1680 | Delay - Culvert - EWN 11 - approval needed | 16-Feb-26* | 2026-03-05 | 14.00d | 32.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1660 | GI Tunnel Route Shaft 2 -3 - Broadwater Woods - 1 BH in Woods, 1 BH after Road Crossing, 1 Piezecone (CPTu) | 2026-03-06 | 2026-04-02 | 20.00d | 32.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1670 | Ground Investigation Shaft 3 - Cardinal Allen High School - 1 Indicative Piezecone (CPTu) | 2026-03-03 | 2026-03-30 | 20.00d | 35.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1690 | Ground Investigation Shaft 5 - West Way - 1 BH, 1 Piezecone (CPTu), 1 CBR By Dynamic Cone Penetration | 2026-01-26 | 2026-02-25 | 23.00d | 33.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1750 | Ground Investigation Report 5-7 | 2026-02-26 | 2026-04-01 | 25.00d | 33.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1770 | On Site Initial Survey | 2026-01-14 | 2026-01-14 | 1.00d | 227.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1780 | Meeting Bowland. Murphy and UU to agree Survey Strategy | 2026-01-15 | 2026-01-15 | 1.00d | 227.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1300 | Initial surveys and desktop studies | 2026-01-27 | 2026-02-12 | 13.00d | 227.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2560 | Share Proposals with LPA Planners | 2026-01-27 | 2026-01-27 | 1.00d | 227.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1790 | UU Mtg - Natural England HRA Migration Strategy | 2026-01-28 | 2026-01-28 | 1.00d | 227.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2550 | UU - Wyre Tree Officer Consultation/Agreement - Agree Compensation | 2026-01-28 | 2026-02-19 | 17.00d | 505.38d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2570 | Produce HRA for tree clearance, GI and site Enabling works | 2026-01-30 | 2026-02-19 | 15.00d | 227.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1460 | Delay - Treefelling - EWN 16 | 16-Feb-26* | 2026-02-18 | 3.00d | 223.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1380 | Broadwater Tree Clearance (with watching brief) | 2026-02-19 | 2026-02-25 | 5.00d | 223.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2580 | Ecology Surveys Complete |  | 2026-02-25 | 0.00d | 223.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-1000 | Outline Design | 2026-01-22 | 2026-04-01 | 50.00d | 18.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2085 | Contractor Confirmation | 2026-01-22 | 2026-01-30 | 7.00d | 30.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2010 | Agree Boreholes Sequence - Programme | 22-Jan-26* | 2026-01-23 | 2.00d | 18.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2190 | Complete Utilities Desktop Survey | 2026-01-26 | 2026-01-26 | 1.00d | 35.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2050 | Confirm Contractor GI Test Requirement | 2026-01-30 | 2026-01-30 | 1.00d | 38.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2091 | Confirm S1/S2 Alignment Following National Highways Engagement | 13-Feb-26* | 2026-02-13 | 1.00d | 29.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2150 | Delay - Landfill site Issue - EWN18 | 2026-02-16 | 2026-03-06 | 15.00d | 29.00d | JMS-P3-5d BH+2x - November 2023
AMP8-DD&B-ROS-OUD-2140 | Create Geotech Long Section | 2026-03-09 | 2026-03-09 | 1.00d | 29.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2170 | Complete LIDAR Survey | 2026-03-12 | 2026-03-12 | 1.00d | 29.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2020 | Known Materials List | 2026-01-22 | 2026-01-26 | 3.00d | 23.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2200 | Confirm Whether or not to Grout Annulus | 2026-01-26 | 2026-01-26 | 1.00d | 35.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2095 | Confirm Perm Shaft/Temp Shafts. | 2026-01-27 | 2026-01-27 | 1.00d | 23.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2070 | Concept Design Shaft 7 (Tie In Downstream) | 2026-01-28 | 2026-01-28 | 1.00d | 23.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2100 | Complete Pipework Long Section for Hyadraulic Review | 2026-01-28 | 2026-01-29 | 2.00d | 30.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2120 | Concept Design Shaft 7 (Tie In Upstream) | 2026-01-29 | 2026-02-02 | 3.00d | 23.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2060 | Complete Design for Product Pipe Materials | 2026-01-30 | 2026-02-02 | 2.00d | 30.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2040 | No of TBM Confirmation 6 feb | 2026-02-03 | 2026-02-03 | 1.00d | 54.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2110 | Commence Trenchless ECI Period 3fe | 2026-02-03 | 2026-03-02 | 20.00d | 30.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2160 | Shaft 7 Design Endorsed 12 FEB | 2026-03-11 | 2026-03-11 | 1.00d | 29.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2180 | Decide Tunnel Levels Invert and Grade 13 Feb | 2026-03-12 | 2026-03-12 | 0.00d | 30.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2260 | Complete Pipe Jacking Design (Spec Settlement) | 13-Mar-26* | 2026-03-13 | 1.00d | 29.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2290 | GBR Document 2 weeks prior to Tunnelling Commencing | 16-Mar-26* | 2026-03-16 | 1.00d | 29.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2270 | Submit Design to National Highways | 2026-03-18 | 2026-03-20 | 3.00d | 36.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2210 | Undertake Advanced GPR Survey 200m section adj to Fairway (to prove GRP/DI) | 2026-02-06 | 2026-02-09 | 2.00d | 23.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2090 | Undertake Enhanced GPR Survey Trial (Identify GPR/DI Interface) | 2026-02-10 | 2026-02-24 | 11.00d | 23.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2130 | Confirm Presence of GRP of Fairway Leg | 2026-02-26 | 2026-03-04 | 5.00d | 38.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2300 | Complete GPR Survey |  | 2026-03-04 | 0.00d | 38.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-TWD-2150 | Engage Sheet Piling Contractor TW Design | 2026-02-13 | 2026-03-02 | 12.00d | 23.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-TWD-2280 | Sheet Piling TW Design Complete |  | 2026-03-02 | 0.00d | 23.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1080 | Place Order Standard Container Cabins | 2026-01-12 | 2026-01-16 | 5.00d | 52.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1090 | Lead In Standard Container Cabins | 2026-01-19 | 2026-02-06 | 15.00d | 52.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2020 | Mobilisation | 2026-03-03 | 2026-03-09 | 5.00d | 33.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-EW-2010 | Trial Holes & Route Proving | 2026-02-03 | 2026-02-23 | 15.00d | 15.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-6400 | Install Standard Container Cabins | 06-Mar-26* | 2026-03-17 | 7.00d | 32.50d | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-1030 | Cable up cabins | 2026-03-17 | 2026-03-20 | 3.00d | 32.50d | Enterprise 5d Workweek
AMP8-DD&B-ROS-MIL-2520 | Project Start | 2026-01-26 |  | 0.00d | 1.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-1140 | Access Granted Shaft 4 Cardinal Allen High School | 2026-02-16 |  | 0.00d | 19.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-6340 | Cardinal Allen High School Mid Term Closure | 16-Feb-26* | 2026-02-19 | 4.00d | 19.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-6330 | Cardinal Allen High School Closes & Staff Inset day | 26-Mar-26* | 2026-03-27 | 2.00d | 33.13d | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-1070 | Create Stone Working Platform - 100m x 30m | 2026-01-27 | 2026-02-24 | 21.00d | 0.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1120 | Access Granted Shaft 7 West Way | 2026-01-27 |  | 0.00d | 0.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-1060 | Create Bellmouth Entrance | 2026-02-25 | 2026-03-02 | 4.00d | 17.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1080 | Hoarding - 260m Shaft 7 | 2026-02-25 | 2026-03-31 | 25.00d | 28.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1110 | Access Granted Shaft 5 West Way | 2026-01-27 |  | 0.00d | 0.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6030 | Create Stone Working Platform - 130m x 30m | 2026-01-27 | 2026-02-26 | 23.00d | 0.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6040 | Hoarding - 320m Shaft 5 | 2026-02-17 | 2026-03-18 | 22.00d | 23.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6020 | Create Bellmouth Entrance | 2026-02-25 | 2026-03-03 | 5.00d | 17.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2600 | Install Trackmatting | 14-Feb-26* | 2026-02-20 | 7.00d | 34.00d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-1100 | Establish Access Shaft 2 &3 Cardinal Allen High School | 2026-02-16 |  | 0.00d | 19.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2580 | Install Traffic Management | 2026-02-16 | 2026-02-16 | 1.00d | 19.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2590 | Install Herras Fencing | 2026-02-16 | 2026-02-20 | 5.00d | 19.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1270 | Install Hoarding (Including Weekend Working) - Approx 500m | 2026-02-24 | 2026-03-30 | 25.00d | 23.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1280 | Install Haul Road From Corner of Melbourne Avenue To Shaft 4 - 350m | 2026-02-27 | 2026-03-12 | 10.00d | 15.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2610 | Install Dropped Kerb & Access | 2026-03-04 | 2026-03-12 | 7.00d | 17.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1290 | Create Common Shaft Compound Between Shaft 3 & 4 | 2026-03-06 | 2026-04-02 | 20.00d | 15.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1720 | UU PRoW closure/diversion needs to be facilitated | 2026-02-04 | 2026-02-18 | 11.00d | 42.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2550 | Needle Sweep | 2026-02-04 | 2026-02-06 | 3.00d | 5.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2620 | UU Close Footpath - | 04-Feb-26* | 2026-02-18 | 11.00d | 8.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6090 | Delay - Tree clearance - EWN 16 | 16-Feb-26* | 2026-02-18 | 3.00d | 0.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1300 | Tree Clearance (Under Ecology watching brief) | 2026-02-19 | 2026-02-26 | 6.00d | 36.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2560 | Establish TM | 2026-02-19 | 2026-02-19 | 1.00d | 29.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2630 | Install Herras Fencing | 19-Feb-26* | 2026-02-20 | 2.00d | 40.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6080 | Establish Initial Access for Tree Clearance Shaft 2 Broadwater Woods | 2026-02-19 | 2026-02-19 | 1.00d | 41.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1310 | Access Road In To Site - 200m Long | 2026-02-27 | 2026-03-12 | 10.00d | 36.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1320 | Create Stone Working Platform - 50m x 50m | 2026-03-13 | 2026-03-26 | 10.00d | 36.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1090 | Access Shaft 1 Fleetwood Works | 2026-02-04 |  | 0.00d | 39.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-2640 | UU National Highways Mtg & agree traffic management | 13-Feb-26* | 2026-02-13 | 1.00d | 32.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2570 | UU Prepare and Issue Notice | 2026-02-19 | 2026-02-25 | 5.00d | 29.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2650 | Notice period & Implementation | 2026-02-26 | 2026-03-11 | 10.00d | 29.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1340 | Create Compound Entry Point Off A585 - Amounderness Way | 2026-03-12 | 2026-03-25 | 10.00d | 29.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1350 | Create Stone Working Platform - 50m x 50m | 2026-03-26 | 2026-04-10 | 10.00d | 29.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1370 | Jacking Collar - Excavate, Cutting Edge, Ring Build, Wrap Shutter, Steel Reinforcement, Concrete | 2026-02-27 | 2026-03-16 | 15.00d | 0.00d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1410 | Jacking Collar - Excavate, Cutting Edge, Ring Build, Wrap Shutter, Steel Reinforcement, Concrete | 2026-02-25 | 2026-03-13 | 15.00d | 0.00d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1450 | Jacking Collar - Excavate, Cutting Edge, Ring Build, Wrap Shutter, Steel Reinforcement, Concrete | 2026-03-13 | 2026-03-30 | 15.00d | 18.00d | ENT 6 Day Working