## Sheet1
Activity ID | Activity Name | Start | Finish | Remaining Duration | Total Float | Calendar
AMP8-DD&B-ROS-MIL-1000 | Contract Award | 2025-11-24 |  | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-MIL-1010 | Start Construction | 2026-01-26 |  | 0.00d |  | Enterprise 5d Workweek
CANATXX GAS STORAGE LIMITED - Shaft 1, BH101 and BH102 in Title No. LAN40592 |  | 2026-01-05 | 26-Jan-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-1510 | Produce 168 Drawings and Issue to UU | 2026-01-05 | 15-Jan-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-1190 | Section 168 - Power to Access to Carry Out Surveys Shaft 1 (Fleetwood Works) | 2026-01-19 | 26-Jan-26 A | 0.00d |  | ENT 7 Day Working
THE SECRETARY OF STATE FOR TRANSPORT - Access to Shaft, BH101 & BH102 in land Title No. LAN93912 |  | 2026-01-05 | 25-Jan-26 A | 0.00d
AMP8-DD&B-ROS-ECI-1810 | Produce 168 Drawings and Issue to UU | 2026-01-05 | 15-Jan-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-1830 | Section 168 - Power to Access to Carry Out Surveys Shaft 1 (Fleetwood Works) | 2026-01-19 | 25-Jan-26 A | 0.00d |  | ENT 7 Day Working
NATIONAL HIGHWAYS LIMITED - Access to Shaft off Amounderness way. Title No. LA763689 |  | 2026-01-12 | 26-Jan-26 A | 0.00d
AMP8-DD&B-ROS-ECI-1840 | Produce 168 Drawings and Issue to UU | 2026-01-12 | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1860 | Section 168 - Power to Access to Carry Out Surveys Shaft 1 (Fleetwood Works) | 2026-01-20 | 26-Jan-26 A | 0.00d |  | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-1220 | Application and Agreement to close public footpath (Broadwater Wood Shaft 2) | 2025-11-24 | 02-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
WYRE BOROUGH COUNCIL - Shaft 2, BH103, BH104 and BH105 are all within Title No. LAN31003 |  | 2026-01-12 | 26-Jan-26 A | 0.00d
AMP8-DD&B-ROS-ECI-1870 | Produce 168 Drawings and Issue to UU | 2026-01-12 | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1230 | Section 168 - Power to Access to Carry Out Surveys Shaft 2 ( (Broadwater Woods) | 2026-01-20 | 26-Jan-26 A | 0.00d |  | Enterprise 7d Calendar
THE LANCASHIRE COUNTY COUNCIL - Access to Shaft 2, BH103, BH104 and BH105 is via. Title No. LAN96754 |  | 2026-01-12 | 26-Jan-26 A | 0.00d
AMP8-DD&B-ROS-ECI-1890 | Produce 168 Drawings and Issue to UU | 2026-01-12 | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1910 | Section 168 - Power to Access to Carry Out Surveys Shaft 2 ( (Broadwater Woods) | 2026-01-20 | 26-Jan-26 A | 0.00d |  | Enterprise 7d Calendar
UNKOWN LANDOWNER - Access is also via an unnamed parcel of land |  | 2026-01-12 | 26-Jan-26 A | 0.00d
AMP8-DD&B-ROS-ECI-1920 | Produce 168 Drawings and Issue to UU | 2026-01-12 | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1940 | Section 168 - Power to Access to Carry Out Surveys Shaft 2 ( (Broadwater Woods) | 2026-01-20 | 26-Jan-26 A | 0.00d |  | Enterprise 7d Calendar
WYRE BOROUGH COUNCIL - BH 106 and CPT 101 are within Title No. LAN31019 |  | 2026-01-12 | 26-Jan-26 A | 0.00d
AMP8-DD&B-ROS-ECI-1960 | Produce 168 Drawings and Issue to UU | 2026-01-12 | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1950 | Section 168 - Power to Access to Carry Out Surveys Shaft 2 ( (Broadwater Woods) | 2026-01-20 | 26-Jan-26 A | 0.00d |  | Enterprise 7d Calendar
THE LANCASHIRE CC - BH107, BH108, BH109, BH110 and CPT102 are within Title No. LAN81504 |  | 2026-01-12 | 26-Jan-26 A | 0.00d
AMP8-DD&B-ROS-ECI-1980 | Produce 168 Drawings and Issue to UU | 2026-01-12 | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2000 | Section 168 - Power to Access to Carry Out Surveys Shaft 3 & 4 Cardinal Allen Catholic High School Playing Fields | 2026-01-20 | 26-Jan-26 A | 0.00d |  | Enterprise 7d Calendar
LANCASTER ROMAN CATHOLIC DIOCESAN TRUSTEES - land off Melbourne Avenue |  | 2026-01-12 | 26-Jan-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2010 | Produce 168 Drawings and Issue to UU | 2026-01-12 | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2030 | Section 168 - Power to Access to Carry Out Surveys Shaft 3 & 4 Cardinal Allen Catholic High School Playing Fields | 2026-01-20 | 26-Jan-26 A | 0.00d |  | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-2070 | Produce 168 Drawings and Issue to UU | 2026-01-05 | 15-Jan-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-2090 | Section 168 - Power to Access to Carry Out Surveys - Tramway | 2026-01-19 | 26-Jan-26 A | 0.00d |  | ENT 7 Day Working
ELECTRICITY NORTH WEST LIMITED - Electricity Sub station land at South Strand LAN56055 |  | 2026-01-05 | 25-Jan-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-2100 | Produce 168 Drawings and Issue to UU | 2026-01-05 | 15-Jan-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-2120 | Section 168 - Power to Access to Carry Out Surveys - ENW | 2026-01-19 | 25-Jan-26 A | 0.00d |  | ENT 7 Day Working
THE CORPORATION OF ROSSALL SCHOOL - BH111 - BH118, CPT103, CPT104, CBR 10 &102 in Title No. LAN86570 |  | 05-Jan-26 A | 26-Jan-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-2040 | Produce 168 Drawings and Issue to UU | 05-Jan-26 A | 15-Jan-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-2060 | Section 168 - Power to Access to Carry Out Surveys Shaft 5,6 & 7 - Rossall School | 20-Jan-26 A | 26-Jan-26 A | 0.00d |  | ENT 7 Day Working
CANATXX GAS STORAGE LIMITED - Shaft 1, BH101 and BH102 in Title No. LAN40592 |  | 14-Jan-26 A | 21-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2160 | Produce 159 Drawings and Issue to UU | 14-Jan-26 A | 21-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2170 | UU Serve Notice to Landowner | 21-Jan-26 A | 21-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2510 | Land Owner Agrees Early Entry | 21-Jan-26 A |  | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2130 | Section 159 - Power to Access for Permanent Works Shaft 1 (Fleetwood Works) | 22-Jan-26 A | 21-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
THE SECRETARY OF STATE FOR TRANSPORT - Access to Shaft, BH101 & BH102 in land Title No. LAN93912 |  | 13-Jan-26 A | 12-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2190 | Produce 159 Drawings and Issue to UU | 13-Jan-26 A | 21-Jan-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-ECI-2200 | UU Serve Notice to Landowner | 22-Jan-26 A | 03-Feb-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-ECI-2180 | Section 159 - Power to Access for Permanent Works Shaft 1 (Fleetwood Works) | 09-Feb-26 A | 12-Apr-26 A | 0.00d |  | ENT 7 Day Working
NATIONAL HIGHWAYS LIMITED - Access to Shaft off Amounderness way. Title No. LA763689 |  | 13-Jan-26 A | 27-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2220 | Produce 159 Drawings and Issue to UU | 13-Jan-26 A | 21-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2230 | UU Serve Notice to Landowner | 22-Jan-26 A | 27-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2210 | Section 159 - Power to Access for Permanent Works Shaft 1 (Fleetwood Works) | 28-Jan-26 A | 27-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
WYRE BOROUGH COUNCIL - Shaft 2, BH103, BH104 and BH105 are all within Title No. LAN31003 |  | 14-Jan-26 A | 27-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2240 | Produce 159 Drawings and Issue to UU | 14-Jan-26 A | 20-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2250 | UU Serve Notice to Landowner | 21-Jan-26 A | 27-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2150 | Section 159 - Power to Access for Permanent Works Shaft 2 ( (Broadwater Woods) | 28-Jan-26 A | 27-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
THE LANCASHIRE COUNTY COUNCIL - Access to Shaft 2, BH103, BH104 and BH105 is via. Title No. LAN96754 |  | 2026-01-14 | 03-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2270 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 20-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2280 | UU Serve Notice to Landowner | 2026-01-21 | 02-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2260 | Section 159 - Power to Access for Permanent Works Shaft 2 ( (Broadwater Woods) | 2026-02-03 | 03-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
UNKOWN LANDOWNER - Access is also via an unnamed parcel of land |  | 14-Jan-26 A | 26-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2300 | Produce 159 Drawings and Issue to UU | 14-Jan-26 A | 21-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2310 | UU Serve Notice to Landowner | 22-Jan-26 A | 26-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2290 | Section 159 - Power to Access to for Permanent Works Shaft 2 ( (Broadwater Woods) | 27-Jan-26 A | 26-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
WYRE BOROUGH COUNCIL - BH 106 and CPT 101 are within Title No. LAN31019 |  | 14-Jan-26 A | 27-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2330 | Produce 159 Drawings and Issue to UU | 14-Jan-26 A | 21-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2340 | UU Serve Notice to Landowner | 22-Jan-26 A | 27-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2320 | Section 159 - Power to Access to for Permanent Works Shaft 2 ( (Broadwater Woods) | 28-Jan-26 A | 27-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-1570 | WYRE BOROUGH COUNCIL - King Georges Playing Fields - RL Boundary, no boreholes | 14-Jan-26 A | 23-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
THE LANCASHIRE CC - BH107, BH108, BH109, BH110 and CPT102 are within Title No. LAN81504 |  | 14-Jan-26 A | 27-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2360 | Produce 159 Drawings and Issue to UU | 14-Jan-26 A | 20-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2370 | UU Serve Notice to Landowner | 21-Jan-26 A | 27-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2500 | Land Owner Agrees Early Entry | 21-Jan-26 A |  | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2350 | Section 159 - Power to Access to for Permanent Works Shaft 3 & 4 Cardinal Allen Catholic High School Playing Fields | 28-Jan-26 A | 27-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
LANCASTER ROMAN CATHOLIC DIOCESAN TRUSTEES - land off Melbourne Avenue |  | 14-Jan-26 A | 27-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2390 | Produce 159 Drawings and Issue to UU | 14-Jan-26 A | 20-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2400 | UU Serve Notice to Landowner | 21-Jan-26 A | 27-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2520 | Land Owner Agrees Early Entry | 21-Jan-26 A |  | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2380 | Section 159 - Power to Access for Permanent Works Shaft 3 & 4 Cardinal Allen Catholic High School Playing Fields | 28-Jan-26 A | 27-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
BLACKPOOL BOROUGH COUNCIL - Tramway LAN78634 |  | 14-Jan-26 A | 27-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2450 | Produce 159 Drawings and Issue to UU | 14-Jan-26 A | 20-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2460 | UU Serve Notice to Landowner | 21-Jan-26 A | 27-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2440 | Section 159 - Power to Access for Permanent Works - Tramway | 28-Jan-26 A | 27-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
ELECTRICITY NORTH WEST LIMITED - Electricity Sub station land at South Strand LAN56055 |  | 14-Jan-26 A | 27-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2480 | Produce 159 Drawings and Issue to UU | 14-Jan-26 A | 20-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2490 | UU Serve Notice to Landowner | 21-Jan-26 A | 27-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2470 | Section 159 - Power to Accessfor Permanent Works - ENW | 2026-01-28 | 27-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-2540 | Access Protection Survey Required | 2026-01-28 | 03-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
Shaft 5 &7 |  | 2026-01-14 | 29-Apr-26 A | 0.00d
THE CORPORATION OF ROSSALL SCHOOL - BH111 - BH118, CPT103, CPT104, CBR 10 &102 in Title No. LAN86570 |  | 2026-01-14 | 29-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2420 | Produce 159 Drawings and Issue to UU | 2026-01-14 | 20-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2430 | UU Serve Notice to Landowner | 2026-01-21 | 29-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2530 | Land Owner Agrees Early Entry | 2026-01-21 |  | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2410 | Section 159- Power to Access for Permanent Works Shaft 5 & 7 - Rossall School | 2026-01-30 | 29-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
AMP8-DD&B-ROS-ECI-2590 | UU Prepare and Issue Section 61 | 2026-04-20 | 24-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2620 | Section 61- Approval - Shaft 1 | 2026-04-25 |  | 0.00d |  | Enterprise 7d Calendar
Shaft 2 |  | 2026-04-20 | 25-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2630 | UU Prepare and Issue Section 61 | 2026-04-20 | 24-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2650 | Section 61- Approval - Shaft 2 | 2026-04-25 |  | 0.00d |  | Enterprise 7d Calendar
Shaft 3 |  | 2026-04-20 | 25-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2660 | UU Prepare and Issue Section 61 | 20-Apr-26 A | 24-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2680 | Section 61- Approval - Shaft 3 | 25-Apr-26 A |  | 0.00d |  | Enterprise 7d Calendar
Shaft 4 |  | 20-Apr-26 A | 25-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2690 | UU Prepare and Issue Section 61 | 20-Apr-26 A | 24-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2710 | Section 61- Approval - Shaft 4 | 25-Apr-26 A |  | 0.00d |  | Enterprise 7d Calendar
Shaft 5 |  | 20-Apr-26 A | 25-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2720 | UU Prepare and Issue Section 61 | 20-Apr-26 A | 24-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2740 | Section 61- Approval - Shaft 5 | 25-Apr-26 A |  | 0.00d |  | Enterprise 7d Calendar
Shaft 7 |  | 20-Apr-26 A | 25-Apr-26 A | 0.00d
AMP8-DD&B-ROS-ECI-2750 | UU Prepare and Issue Section 61 | 20-Apr-26 A | 24-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2770 | Section 61- Approval - Shaft 7 | 25-Apr-26 A |  | 0.00d |  | Enterprise 7d Calendar
Ground Investigation Shaft Boreholes |  | 26-Jan-26 A | 16-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Shaft 7 West Way |  | 26-Jan-26 A | 11-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1390 | Ground Investigation - Shaft 7 West Way - 2 Boreholes | 26-Jan-26 A | 19-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1450 | Ground Investigation Report | 20-Feb-26 A | 11-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
Shaft 5 West Way |  | 28-Jan-26 A | 11-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1370 | Ground Investigation Shaft 5 - West Way - 2 Boreholes | 28-Jan-26 A | 20-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1430 | Ground Investigation Report | 23-Feb-26 A | 11-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
Shaft 4 Cardinal Allen High School |  | 23-Feb-26 A | 14-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1360 | Ground Investigation Shaft 4 Cardinal Allen High School - 2 Boreholes | 23-Feb-26 A | 20-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1420 | Ground Investigation Report | 23-Mar-26 A | 14-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Shaft 3 Cardinal Allen High School |  | 03-Mar-26 A | 27-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1350 | Ground Investigation Shaft 3 - Cardinal Allen High School - 2 Boreholes | 03-Mar-26 A | 13-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1410 | Ground Investigation Report | 16-Mar-26 A | 27-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
Shaft 2 BroadWater Wood |  | 23-Mar-26 A | 14-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1340 | Ground Investigation Shaft 2 - Broadwater Woods - 2 Boreholes | 23-Mar-26 A | 26-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1400 | Ground Investigation Report | 27-Mar-26 A | 14-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Shaft 1 Fleetwood Works |  | 12-Mar-26 A | 16-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1170 | Ground Investigation Shaft 1 - Fleetwood Works- 2 no Boreholes | 12-Mar-26 A | 03-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1180 | Ground Investigation Report | 07-Apr-26 A | 16-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Ground InvestigationTunnels |  | 26-Jan-26 A | 29-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Tunnel Amounderness Way - King George Playing Fields Shaft 3 |  | 10-Mar-26 A | 29-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1660 | GI Tunnel Route Shaft 2 -3 - Broadwater Woods - 1 BH in Woods, 1 BH after Road Crossing, 1 Piezecone (CPTu) | 10-Mar-26 A | 13-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1720 | Ground Investigation Report 2-3 | 16-Mar-26 A | 29-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2780 | GI Tunnel Route Shaft 2 -3 - Broadwater Woods - 105 | 2026-03-27 | 03-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Tunnel King George Playing Fields Shaft 3 - King George Playing Fields Shaft 4 |  | 2026-03-09 | 07-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1670 | Ground Investigation Shaft 3 - Cardinal Allen High School - 1 Indicative Piezecone (CPTu) | 2026-03-09 | 13-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1730 | Ground Investigation Report 4 | 2026-03-14 | 07-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Tunnel King George Playing Fields Shaft 4 - King George Playing Fields Shaft 5 |  | 2026-03-16 | 07-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1740 | Ground Investigation Report 4-5 | 2026-03-16 | 07-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1690 | Ground Investigation Shaft 5 - West Way - 1 BH, 1 Piezecone (CPTu), 1 CBR By Dynamic Cone Penetration | 2026-01-26 | 25-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1750 | Ground Investigation Report 5-7 | 2026-02-26 | 16-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2790 | Ground Investigation - BH 119 - West Way | 2026-03-31 | 13-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Ecology Surveys - Bowland Ecology |  | 2026-01-14 | 25-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1770 | On Site Initial Survey | 2026-01-14 | 14-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1780 | Meeting Bowland. Murphy and UU to agree Survey Strategy | 2026-01-15 | 15-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1300 | Initial surveys and desktop studies | 2026-01-27 | 12-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2560 | Share Proposals with LPA Planners | 2026-01-27 | 27-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1790 | UU Mtg - Natural England HRA Migration Strategy | 2026-01-28 | 28-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2550 | UU - Wyre Tree Officer Consultation/Agreement - Agree Compensation | 2026-01-28 | 19-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2570 | Produce HRA for tree clearance, GI and site Enabling works | 2026-01-30 | 19-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1380 | Broadwater Tree Clearance (with watching brief) | 2026-02-19 | 25-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-2580 | Ecology Surveys Complete |  | 25-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1490 | Access to Cardinal Allen restricted - shaft 3&4 -EWN 13 | 2026-01-26 | 14-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1470 | Historic Landfill site issue - shaft 3 - EWN 18 | 2026-02-04 | 27-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1200 | Historic Landfill site issue- shaft 1 - EWN 18 | 2026-02-16 | 27-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1440 | Historic Landfill site Issue - shaft 2 - EWN18 | 2026-02-16 | 27-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1460 | Delay - Treefelling - EWN 16 | 2026-02-16 | 18-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1680 | Existing Culvert in King George - EWN 11 | 2026-02-16 | 16-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1480 | Cadnit Gas pipe - shaft2 - EWN | 2026-03-04 | 19-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1240 | Japanese knotweed - shaft 1- EWN 29 | 2026-03-08 | 20-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-ECI-1250 | National Highway - period to gain access to tunnel beneath - EWN 15 | 2026-04-20 | 2026-05-11 | 6.00d | 9.00d | Enterprise 5d Workweek
Design |  | 2026-01-22 | 2026-06-09 | 26.00d | 50.00d | Enterprise 5d Workweek
Outline Design |  | 2026-01-22 | 2026-05-11 | 6.00d | 29.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-1000 | Outline Design | 2026-01-22 | 10-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2085 | Contractor Confirmation | 2026-01-22 | 30-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
GI - Shafts |  | 2026-01-22 | 2026-05-11 | 0.00d | 29.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2010 | Agree Boreholes Sequence - Programme | 2026-01-22 | 23-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2190 | Complete Utilities Desktop Survey | 2026-01-26 | 26-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2050 | Confirm Contractor GI Test Requirement | 2026-01-30 | 30-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2091 | Confirm S1/S2 Alignment Following National Highways Engagement | 2026-02-13 | 13-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2150 | Delay - Landfill site Issue - EWN18 | 2026-02-16 | 02-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2140 | Create Geotech Long Section | 2026-03-16 | 16-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2170 | Complete LIDAR Survey | 2026-03-17 | 17-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2320 | Complete GI Final Factual |  | 2026-05-11 | 0.00d | 29.00d | Enterprise 5d Workweek
Shaft & Tunnel Design |  | 22-Jan-26 A | 2026-05-11 | 6.00d | 9.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2020 | Known Materials List | 22-Jan-26 A | 26-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2200 | Confirm Whether or not to Grout Annulus | 26-Jan-26 A | 26-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2095 | Confirm Perm Shaft/Temp Shafts. | 27-Jan-26 A | 27-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2070 | Concept Design Shaft 7 (Tie In Downstream) | 28-Jan-26 A | 28-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2100 | Complete Pipework Long Section for Hyadraulic Review | 28-Jan-26 A | 29-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2120 | Concept Design Shaft 7 (Tie In Upstream) | 29-Jan-26 A | 02-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2060 | Complete Design for Product Pipe Materials | 30-Jan-26 A | 02-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2040 | No of TBM Confirmation 6 feb | 03-Feb-26 A | 03-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2110 | Commence Trenchless ECI Period 3fe | 03-Feb-26 A | 10-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2160 | Shaft 7 Design Endorsed | 04-Mar-26 A | 04-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2180 | Decide Tunnel Levels Invert and Grade | 05-Mar-26 A | 25-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2260 | Complete Pipe Jacking Design (Spec Settlement) | 26-Mar-26 A | 13-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2290 | GBR Document 2 weeks prior to Tunnelling Commencing | 02-Apr-26 A | 02-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2270 | Submit Design to National Highways | 20-Apr-26 A | 20-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2330 | National Highway - period to gain access to tunnel beneath | 20-Apr-26 A | 2026-05-11 | 6.00d | 9.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2310 | National Highways Approval Complete |  | 2026-05-11 | 0.00d | 9.00d | Enterprise 5d Workweek
GPR Survey |  | 06-Feb-26 A | 02-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2210 | Undertake Advanced GPR Survey 200m section adj to Fairway (to prove GRP/DI) | 06-Feb-26 A | 09-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2090 | Undertake Enhanced GPR Survey Trial (Identify GPR/DI Interface) | 10-Feb-26 A | 24-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2130 | Confirm Presence of GRP of Fairway Leg | 26-Feb-26 A | 02-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-2300 | Complete GPR Survey |  | 02-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Piling Design |  | 09-Mar-26 A | 31-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-0900 | Piling Design start | 09-Mar-26 A |  | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-1005 | Specification / drawing | 09-Mar-26 A | 19-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-1010 | MGE design of pile | 09-Mar-26 A | 27-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-1090 | Design of Guide Wall | 16-Mar-26 A | 20-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-1020 | MAE design approval | 30-Mar-26 A | 31-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
RAMS for piling work |  | 16-Mar-26 A | 30-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-1050 | Prepare RAMS and issue for approval | 16-Mar-26 A | 20-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-1060 | comment on RAMS | 23-Mar-26 A | 24-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-1070 | Revise RAMS | 25-Mar-26 A | 26-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-OUD-1080 | Approve RAMS for construction | 27-Mar-26 A | 30-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
Detailed Design |  | 13-Apr-26 A | 2026-06-09 | 26.00d | 9.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-DES-1010 | Detailed Design | 13-Apr-26 A | 2026-06-09 | 26.00d | 9.00d | Enterprise 5d Workweek
Temp Works Design |  | 13-Feb-26 A | 2026-05-11 | 6.00d | 70.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-TWD-2150 | Engage Sheet Piling Contractor TW Design | 13-Feb-26 A | 06-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-TWD-2000 | Temp Works Design | 20-Feb-26 A | 2026-05-11 | 6.00d | 9.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-TWD-2280 | Sheet Piling TW Design Complete |  | 06-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
Procurement |  | 24-Nov-25 A | 2026-07-24 | 59.00d | 86.00d | Enterprise 5d Workweek
Material |  | 08-Dec-25 A | 2026-07-24 | 59.00d | 49.00d | Enterprise 5d Workweek
Cabins (Murphy) |  | 12-Jan-26 A | 06-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
Standard Container Cabins |  | 12-Jan-26 A | 06-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1080 | Place Order Standard Container Cabins | 12-Jan-26 A | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1090 | Lead In Standard Container Cabins | 19-Jan-26 A | 06-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
1200 DI pipework |  | 08-Dec-25 A | 2026-07-13 | 50.00d | 43.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1470 | Issue ITT | 08-Dec-25 A | 12-Dec-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1480 | Tender period | 15-Dec-25 A | 08-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1490 | Tender Return | 09-Jan-26 A | 28-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1500 | Tender Evaluation Period &Approval | 29-Jan-26 A | 19-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1510 | Place Order Date | 20-Feb-26 A | 27-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1520 | Lead In (14 wks) | 01-Apr-26 A | 2026-07-13 | 50.00d | 43.00d | Enterprise 5d Workweek
Manholes |  | 05-Feb-26 A | 28-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1540 | Issue ITT | 05-Feb-26 A | 05-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1550 | Tender period | 06-Feb-26 A | 18-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1560 | Tender Return | 19-Feb-26 A | 04-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1570 | Tender Evaluation Period &Approval | 05-Mar-26 A | 30-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1580 | Place Order Date | 31-Mar-26 A | 31-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1590 | Lead In | 01-Apr-26 A | 27-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1600 | Mobilisation tie ins | 28-Apr-26 A | 28-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Shafts cutting ring |  | 08-Dec-25 A | 16-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2250 | Issue ITT | 08-Dec-25 A | 08-Dec-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2260 | Tender period | 09-Dec-25 A | 19-Dec-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2270 | Tender Return | 07-Jan-26 A | 20-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2280 | Tender Evaluation Period &Approval | 21-Jan-26 A | 10-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2290 | Place Order Date | 11-Feb-26 A | 11-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2300 | Lead In | 12-Feb-26 A | 13-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2310 | Deliver to site | 16-Feb-26 A | 16-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
Aggregates |  | 26-Jan-26 A | 30-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1030 | Aggregate call off | 26-Jan-26 A | 30-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
Valves for 1200mm |  | 05-Feb-26 A | 2026-07-24 | 59.00d | 48.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2030 | Issue ITT | 05-Feb-26 A | 05-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2040 | Tender period | 06-Feb-26 A | 19-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2050 | Tender Return | 20-Feb-26 A | 05-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2060 | Tender Evaluation Period &Approval | 06-Mar-26 A | 27-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2070 | Place Order Date | 30-Mar-26 A | 30-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2080 | Lead In | 31-Mar-26 A | 2026-07-24 | 59.00d | 48.00d | Enterprise 5d Workweek
Valves (Air Valves) |  | 05-Feb-26 A | 29-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2100 | Issue ITT | 05-Feb-26 A | 05-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2110 | Tender period | 06-Feb-26 A | 18-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2120 | Tender Return | 19-Feb-26 A | 04-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2130 | Tender Evaluation Period &Approval | 05-Mar-26 A | 27-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2140 | Place Order Date | 30-Mar-26 A | 30-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2150 | Lead In | 31-Mar-26 A | 22-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2160 | Deliver to Site Air Valves | 23-Apr-26 A | 29-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Techno covers/Man Covers |  | 09-Feb-26 A | 30-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2170 | Issue ITT | 09-Feb-26 A | 09-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2180 | Tender period | 10-Feb-26 A | 23-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2190 | Tender Return | 24-Feb-26 A | 10-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2200 | Tender Evaluation Period &Approval | 11-Mar-26 A | 31-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2210 | Place Order Date | 01-Apr-26 A | 01-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2220 | Lead In | 01-Apr-26 A | 23-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2230 | Mobilisation | 24-Apr-26 A | 30-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Ready mix concrete |  | 26-Jan-26 A | 30-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2240 | Call Off Order | 26-Jan-26 A | 30-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
piling material - concrete & steel |  | 16-Mar-26 A | 16-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2320 | Obtain Mix design - MGE | 16-Mar-26 A | 20-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2330 | Client mix design approval | 20-Mar-26 A | 26-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2340 | concrete - Call Off Order - MGE | 27-Mar-26 A | 27-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2350 | Order Reinforcement - MGE | 01-Apr-26 A | 01-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2360 | Piling Reinforcement Lead In - MGE | 01-Apr-26 A | 16-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Sub Contractor |  | 24-Nov-25 A | 2026-06-15 | 30.00d | 115.00d | Enterprise 5d Workweek
Tree Surgery/Felling |  | 07-Jan-26 A | 19-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1610 | Issue ITT | 07-Jan-26 A | 09-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1620 | Tender period | 12-Jan-26 A | 14-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1630 | Tender Return | 15-Jan-26 A | 21-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1640 | Tender Evaluation Period &Approval | 22-Jan-26 A | 27-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1650 | Place Order Date | 28-Jan-26 A | 28-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1730 | Delay - Tree officer - EWN 16- waiting meeting with council tree officer | 16-Feb-26 A | 18-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1670 | Mobilisation | 19-Feb-26 A | 19-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
Ecology |  | 15-Dec-25 A | 26-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1680 | Issue ITT | 15-Dec-25 A | 19-Dec-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1690 | Tender period | 07-Jan-26 A | 09-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1700 | Tender Return | 12-Jan-26 A | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1710 | Tender Evaluation Period &Approval | 19-Jan-26 A | 22-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1720 | Place Order Date | 23-Jan-26 A | 23-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1740 | Mobilisation | 26-Jan-26 A | 26-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
Topo & GPR |  | 28-Nov-25 A | 02-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1120 | Issue ITT | 28-Nov-25 A | 28-Nov-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1130 | Tender period | 01-Dec-25 A | 09-Dec-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1140 | Tender Return | 10-Dec-25 A | 08-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1150 | Tender Evaluation Period &Approval | 09-Jan-26 A | 15-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1160 | Place Order Date | 16-Jan-26 A | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1180 | Mobilisation 2nd feb | 19-Jan-26 A | 02-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
Ground Investigation |  | 25-Nov-25 A | 23-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1190 | Issue ITT | 25-Nov-25 A | 25-Nov-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1200 | Tender period | 26-Nov-25 A | 05-Dec-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1210 | Tender Return | 08-Dec-25 A | 19-Dec-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1220 | Tender Evaluation Period &Approval | 07-Jan-26 A | 09-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1230 | Place Order Date | 12-Jan-26 A | 12-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1240 | Lead In | 13-Jan-26 A | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1250 | Mobilisation | 19-Jan-26 A | 23-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
Pipe jacking |  | 07-Jan-26 A | 15-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1260 | Issue ITT | 07-Jan-26 A | 09-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1270 | Tender period | 12-Jan-26 A | 16-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1280 | Tender Return | 19-Jan-26 A | 21-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1290 | Tender Evaluation Period &Approval | 22-Jan-26 A | 11-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1300 | Place Order Date | 12-Feb-26 A | 11-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1000 | Mobilisation Pipe Jacking Subcontractor | 16-Mar-26 A | 15-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Traffic Management |  | 24-Nov-25 A | 28-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1400 | Issue ITT | 24-Nov-25 A | 24-Nov-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1410 | Tender period | 25-Nov-25 A | 08-Dec-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1420 | Tender Return | 09-Dec-25 A | 07-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1430 | Tender Evaluation Period &Approval | 08-Jan-26 A | 21-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1440 | Place Order Date | 22-Jan-26 A | 22-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1460 | Mobilisation TM | 23-Jan-26 A | 28-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
Hoarding |  | 15-Dec-25 A | 16-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1330 | Issue ITT | 15-Dec-25 A | 15-Dec-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1340 | Tender period | 16-Dec-25 A | 12-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1350 | Tender Return | 13-Jan-26 A | 26-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1360 | Tender Evaluation Period &Approval | 27-Jan-26 A | 06-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1370 | Place Order Date | 09-Feb-26 A | 09-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1380 | Lead In | 10-Feb-26 A | 16-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1390 | Mobilisation to Site |  | 16-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
Metalwork/Secondary Steelwork |  | 25-Mar-26 A | 2026-06-15 | 30.00d | 115.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1750 | Issue ITT | 25-Mar-26 A | 10-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1760 | Tender period | 10-Apr-26 A | 30-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1770 | Tender Return | 2026-05-01 | 2026-05-22 | 15.00d | 115.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1780 | Tender Evaluation Period &Approval | 2026-05-26 | 2026-06-15 | 15.00d | 115.00d | Enterprise 5d Workweek
Cover slabs for shafts |  | 09-Feb-26 A | 2026-05-12 | 7.00d | 8.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1820 | Issue ITT | 09-Feb-26 A | 20-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1830 | Tender period | 23-Feb-26 A | 09-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1840 | Tender Return | 09-Mar-26 A | 20-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1850 | Tender Evaluation Period &Approval | 23-Mar-26 A | 17-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1860 | Place Order Date | 20-Apr-26 A | 20-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1870 | Lead In | 21-Apr-26 A | 2026-05-05 | 2.00d | 8.00d | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1880 | Mobilisation 6 july SOS | 2026-05-06 | 2026-05-12 | 5.00d | 8.00d | Enterprise 5d Workweek
Surfacing |  | 09-Feb-26 A | 23-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1890 | Issue ITT | 09-Feb-26 A | 09-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1900 | Tender period | 10-Feb-26 A | 23-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1910 | Tender Return | 24-Feb-26 A | 09-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1920 | Tender Evaluation Period &Approval | 10-Mar-26 A | 30-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1930 | Place Order Date | 31-Mar-26 A | 31-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1940 | Lead In | 01-Apr-26 A | 16-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1950 | Mobilisation | 20-Apr-26 A | 23-Apr-26 A | 0.00d |  | Enterprise 5d Workweek
Landscaping |  | 15-Dec-25 A | 20-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1960 | Issue ITT | 15-Dec-25 A | 15-Dec-25 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1970 | Tender period | 16-Dec-25 A | 14-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1980 | Tender Return | 15-Jan-26 A | 23-Jan-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-1990 | Tender Evaluation Period &Approval | 26-Jan-26 A | 05-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2000 | Place Order Date 6th Feb | 06-Feb-26 A | 09-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2010 | Lead In | 10-Feb-26 A | 09-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2020 | Mobilisation | 16-Mar-26 A | 20-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2370 | Issue ITT | 09-Mar-26 A | 09-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2380 | Tender period | 10-Mar-26 A | 16-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2390 | Tender Return | 16-Mar-26 A | 20-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2400 | Tender Evaluation Period &Approval | 23-Mar-26 A | 25-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2410 | Place Order | 26-Mar-26 A | 26-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-PROC-2420 | Movement order lead period | 27-Mar-26 A | 31-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-EW-2010 | Trial Holes & Route Proving | 03-Feb-26 A | 23-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-6400 | Install Standard Container Cabins | 16-Mar-26 A | 24-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-1030 | Cable up cabins | 25-Mar-26 A | 27-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-MIL-2520 | Project Start | 26-Jan-26 A |  | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-1140 | Access Granted Shaft 4 Cardinal Allen High School | 16-Feb-26 A |  | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-6340 | Cardinal Allen High School Mid Term Closure | 16-Feb-26 A | 19-Feb-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-6330 | Cardinal Allen High School Closes & Staff Inset day | 26-Mar-26 A | 27-Mar-26 A | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-6350 | Cardinal Allen High School Good Friday & Easter Monday | 03-Apr-26 A | 06-Apr-26 A | 0.00d |  | Enterprise 7d Calendar
AMP8-DD&B-ROS-CON-1070 | Create Stone Working Platform - 100m x 30m | 27-Jan-26 A | 24-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1120 | Access Granted Shaft 7 West Way | 27-Jan-26 A |  | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-1080 | Hoarding - 260m Shaft 7 | 25-Feb-26 A | 10-Apr-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1060 | Create Bellmouth Entrance | 13-Apr-26 A | 17-Apr-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1110 | Access Granted Shaft 5 West Way | 27-Jan-26 A |  | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6030 | Create Stone Working Platform - 130m x 30m | 27-Jan-26 A | 03-Mar-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6040 | Hoarding - 320m Shaft 5 | 17-Feb-26 A | 10-Apr-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6020 | Create Bellmouth Entrance | 13-Apr-26 A | 17-Apr-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2600 | Install Trackmatting | 14-Feb-26 A | 20-Feb-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-1100 | Establish Access Shaft 2 &3 Cardinal Allen High School | 16-Feb-26 A |  | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2580 | Install Traffic Management | 16-Feb-26 A | 16-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2590 | Install Herras Fencing | 16-Feb-26 A | 20-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1270 | Install Hoarding (Including Weekend Working) - Approx 500m | 24-Feb-26 A | 28-Mar-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1280 | Install Haul Road From Corner of Melbourne Avenue To Shaft 4 - 350m | 09-Mar-26 A | 09-Apr-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1290 | Working Platform & welfare shaft 3 | 19-Mar-26 A | 02-Apr-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6470 | Working Platform shaft 4 & piling platform | 10-Apr-26 A | 28-Apr-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2610 | Install Dropped Kerb & Access | 20-Apr-26 A | 24-Apr-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1720 | UU PRoW closure/diversion needs to be facilitated | 04-Feb-26 A | 18-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2550 | Needle Sweep | 04-Feb-26 A | 06-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2620 | UU Close Footpath - | 04-Feb-26 A | 18-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6090 | Delay - Tree clearance - EWN 16 | 16-Feb-26 A | 18-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1300 | Tree Clearance (Under Ecology watching brief) | 19-Feb-26 A | 26-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2560 | Establish TM | 19-Feb-26 A | 19-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2630 | Install Herras Fencing | 19-Feb-26 A | 20-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6080 | Establish Initial Access for Tree Clearance Shaft 2 Broadwater Woods | 19-Feb-26 A | 19-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-1310 | Access Road In To Site - 200m Long | 23-Mar-26 A | 20-Apr-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1320 | Create Stone Working Platform - 50m x 50m | 21-Apr-26 A | 2026-05-05 | 3.00d | 32.52d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1330 | Hoarding - 250m | 2026-05-06 | 2026-05-27 | 15.00d | 61.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-7390 | Create piling Platform - 25m x 25m | 2026-05-06 | 2026-05-13 | 7.00d | 32.52d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1090 | Access Shaft 1 Fleetwood Works | 04-Feb-26 A |  | 0.00d |  | Enterprise 5d Workweek
AMP8-DD&B-ROS-CON-2640 | UU National Highways Mtg & agree traffic management | 13-Feb-26 A | 13-Feb-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2570 | UU Prepare and Issue Notice | 19-Feb-26 A | 20-Mar-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2650 | Notice period & Implementation | 23-Mar-26 A | 07-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6480 | Go/No-Go - Meeting JMS/UU to confirm Shaft 1 requirment | 25-Mar-26 A | 25-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1360 | Hoarding - 250m | 15-Apr-26 A | 26-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7400 | Fencing, Site clearance, leveling and silt fencing | 22-Apr-26 A | 29-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-1350 | construct piling platform 25x25m | 30-Apr-26 A | 2026-05-05 | 5.00d | 8.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-1000 | Diaphragm wall construction | 02-Mar-26 A | 07-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1440 | Excavation inside diaphragm wall | 09-Mar-26 A | 16-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1010 | Blinding Concrete | 16-Mar-26 A | 16-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1020 | Install & Fix the cutting edge | 16-Mar-26 A | 17-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6960 | Build Rings no 1,2 | 17-Mar-26 A | 18-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1040 | Assemble the Jacket shutter | 19-Mar-26 A | 19-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1050 | Concrete the cutting edge | 20-Mar-26 A | 20-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6970 | Remove the Jacket shutter | 21-Mar-26 A | 21-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6980 | Installl Jacking Leg | 22-Mar-26 A | 22-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6990 | Install steel colar cages | 23-Mar-26 A | 23-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6800 | Concrete - Collar - 000m3 | 24-Mar-26 A | 25-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6810 | Ring no 3,4,5,6 - (4 Ring @ 6 days ≈ 1 ring /1.5 d) | 28-Mar-26 A | 12-Apr-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6750 | Ring no 7,8,9,10 (4 Ring @ 6 days ≈ 1 ring /1.5 d) | 13-Apr-26 A | 22-Apr-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6760 | Ring no 11,12,13,14 (4 Ring @ 6 days ≈ 1 ring /1.5 d) | 23-Apr-26 A | 30-Apr-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6770 | Ring no 15,16,17,18 (4 Ring @ 6 days ≈1 ring /1.5 d) | 30-Apr-26 A | 2026-05-07 | 5.00d | 11.50d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6780 | Ring no 19,20,21,22 (4 Ring @ 6 days ≈1 ring /1.5d) | 2026-05-08 | 2026-05-14 | 6.00d | 11.50d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6790 | Ring no 23 ( ≈1 ring /1.5d) | 2026-05-15 | 2026-05-16 | 1.50d | 11.50d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1170 | Concrete Plug - 260 m3 | 2026-05-16 | 2026-05-18 | 1.00d | 11.50d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5810 | Curing time | 2026-05-18 | 2026-05-27 | 7.00d | 17.54d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5820 | Dowel Collar 128No. S32 - 18/d | 2026-05-18 | 2026-05-27 | 7.00d | 18.54d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1200 | Pump out | 2026-05-27 | 2026-05-28 | 1.00d | 17.54d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5830 | Grout Annulus | 2026-05-28 | 2026-05-29 | 1.00d | 17.54d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5840 | Steel Fixing - ≈18.5 ton | 2026-05-29 | 2026-06-02 | 3.00d | 17.54d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5860 | Diaphragm wall construction | 04-Mar-26 A | 09-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1450 | Excavation Inside diaphragm wall | 09-Mar-26 A | 13-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1240 | Install & Fix the cutting edge | 16-Mar-26 A | 19-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5870 | Blinding Concrete | 16-Mar-26 A | 16-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5880 | Build Rings no 1,2 | 19-Mar-26 A | 20-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1260 | Assemble the Jacket shutter | 23-Mar-26 A | 23-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5890 | Concrete the cutting edge | 23-Mar-26 A | 23-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5900 | Remove the Jacket shutter | 24-Mar-26 A | 25-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5910 | Installl Jacking Leg | 26-Mar-26 A | 27-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5920 | Install steel colar cages | 28-Mar-26 A | 30-Mar-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5930 | Concrete - Collar | 31-Mar-26 A | 03-Apr-26 A | 0.00d |  | ENT 6 Day Working
AMP8-DD&B-ROS-CON-5940 | Ring no 3,4,5,6 (4 Ring @ 6 days ≈1 ring /1.5d) | 06-Apr-26 A | 12-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-5950 | Ring no 7,8,9,10 (4 Ring @ 6 days ≈1 ring /1.5d) | 12-Apr-26 A | 21-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-1340 | Ring no 11,12,13,14 (4 Ring @ 6 days ≈1 ring /1.5d) | 22-Apr-26 A | 27-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-5960 | Ring no 15,16,17,18 (4 Ring @ 6 days ≈1 ring /1.5d) | 28-Apr-26 A | 2026-05-03 | 3.00d | 0.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-5970 | Ring no 19,20,21 (4 Ring @ 6 days ≈1 ring /1.5d) | 2026-05-04 | 2026-05-08 | 5.00d | 0.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-5980 | Muck the last ring | 2026-05-09 | 2026-05-10 | 1.50d | 0.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-1390 | Concrete Plug - 260 m3 | 2026-05-10 | 2026-05-11 | 1.00d | 0.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-5990 | Curing time | 2026-05-11 | 2026-05-16 | 5.00d | 0.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6000 | Dowel Collar 128No. S32 - 18/d | 2026-05-11 | 2026-05-16 | 5.00d | 1.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-1420 | Pump out | 2026-05-16 | 2026-05-17 | 1.00d | 0.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6010 | Grout Annulus | 2026-05-17 | 2026-05-18 | 1.00d | 0.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-2540 | Steel Fixing ≈18.5 ton | 2026-05-18 | 2026-05-21 | 3.00d | 0.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6050 | Concrete work - 87 m3 | 2026-05-21 | 2026-05-22 | 1.00d | 0.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6060 | Curing time | 2026-05-22 | 2026-05-25 | 3.00d | 0.50d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6300 | Mobilization 1st Rig to site | 30-Mar-26 A | 31-Mar-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6310 | Mobilization 2nd Rig to site | 23-Apr-26 A | 2026-05-01 | 1.00d | 18.52d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-6530 | Excavate & Blinding - Guide Wall | 26-Mar-26 A | 27-Mar-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6540 | Steel Fixing & Formwork - Guide Wall | 28-Mar-26 A | 30-Mar-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6550 | Concrete - Guide wall | 31-Mar-26 A | 31-Mar-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6560 | Curing time | 01-Apr-26 A | 02-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6570 | Installation Concrete Infill slab | 01-Apr-26 A | 01-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6580 | Steel cages fabrication -22 pile ≈3 cages/d | 02-Apr-26 A | 19-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6590 | Curing time for Infill slab | 02-Apr-26 A | 03-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-2710 | Piling work- 7 soft pile (1.5 pile/d, pile depth ≈ 22m | 05-Apr-26 A | 13-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6490 | Piling work- 7 soft pile (1.5 pile/d, pile depth ≈ 22m | 13-Apr-26 A | 22-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6420 | Piling work- 5 hard pile (1 pile/d, pile depth ≈ 22m | 22-Apr-26 A | 27-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6500 | Piling work- 5 hard pile (1 pile/d, pile depth ≈ 22m | 27-Apr-26 A | 2026-05-02 | 1.54d | 26.30d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6510 | Piling work- 7 soft pile (1.5 pile/d, pile depth ≈ 22m | 2026-05-02 | 2026-05-07 | 4.66d | 26.30d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6450 | Piling work- 5 hard pile (1 pile/d, pile depth ≈ 22m | 2026-05-07 | 2026-05-12 | 5.00d | 26.30d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7410 | Piling work- 3 soft pile (1.5 pile/d, pile depth ≈ 22m | 2026-05-12 | 2026-05-14 | 2.00d | 26.30d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6520 | Piling work- 9 hard pile (1 pile/d, pile depth ≈ 22m | 2026-05-14 | 2026-05-22 | 8.00d | 26.30d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6070 | Demolish & Remove Internal Guide Wall | 2026-05-22 | 2026-05-23 | 1.50d | 26.30d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-5710 | Shaft Excavation- (20m depth ≈1935m3@ ≈12.5 m3/h | 2026-05-23 | 2026-05-30 | 6.45d | 26.68d | ENT 24 hr Working
AMP8-DD&B-ROS-CON-5720 | Blinding Concrete | 2026-05-30 | 2026-05-30 | 1.00d | 26.97d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6670 | Excavate & Blinding - Guide Wall | 29-Apr-26 A | 29-Apr-26 A | 0.00d |  | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6680 | Steel Fixing & Formwork - Guide Wall (internal & External, L=70m | 30-Apr-26 A | 2026-05-02 | 2.00d | 9.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6690 | Concrete - Guide wall | 2026-05-03 | 2026-05-03 | 1.00d | 9.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6700 | Curing time | 2026-05-04 | 2026-05-05 | 2.00d | 9.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6710 | Installation Concrete Infill slab | 2026-05-04 | 2026-05-04 | 1.00d | 9.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6720 | Steel cages fabrication -22 pile ≈3 cages/d | 2026-05-05 | 2026-05-12 | 7.33d | 29.85d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6730 | Curing time for Infill slab | 2026-05-05 | 2026-05-06 | 2.00d | 25.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6600 | Piling work- 7 soft pile (1.5 pile/d, pile depth ≈ 22m | 2026-05-07 | 2026-05-11 | 4.66d | 25.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6610 | Piling work- 5 hard pile (1 pile/d, pile depth ≈ 22m | 2026-05-11 | 2026-05-16 | 5.00d | 25.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6620 | Piling work- 7 soft pile (1.5 pile/d, pile depth ≈ 22m | 2026-05-16 | 2026-05-21 | 4.66d | 25.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6630 | Piling work- 5 hard pile (1 pile/d, pile depth ≈ 22m | 2026-05-21 | 2026-05-26 | 5.00d | 25.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6640 | Piling work- 7 soft pile (1.5 pile/d, pile depth ≈ 22m | 2026-05-26 | 2026-05-30 | 4.66d | 25.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6650 | Piling work- 5 hard pile (1 pile/d, pile depth ≈ 22m | 2026-05-30 | 2026-06-04 | 5.00d | 25.52d | ENT 7 Day Working
Shaft 1 Fleetwood Work |  | 2026-05-06 | 2026-06-01 | 27.00d | 8.75d | ENT 7 Day Working
Guide Wall |  | 2026-05-06 | 2026-05-12 | 7.00d | 9.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7230 | Excavate & Blinding - Guide Wall | 2026-05-06 | 2026-05-06 | 1.00d | 8.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7240 | Steel Fixing & Formwork - Guide Wall (internal & External, L=70m) | 2026-05-07 | 2026-05-09 | 3.00d | 8.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7250 | Concrete - Guide wall | 2026-05-10 | 2026-05-10 | 1.00d | 8.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7260 | Curing time | 2026-05-11 | 2026-05-12 | 2.00d | 9.75d | ENT 7 Day Working
Preparation Work for piling Rig |  | 2026-05-11 | 2026-05-20 | 9.33d | 14.42d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7270 | Installation Concrete Infill slab | 2026-05-11 | 2026-05-12 | 2.00d | 8.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7280 | Steel cages fabrication | 2026-05-13 | 2026-05-20 | 7.33d | 14.42d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7290 | Curing time for Infill slab | 2026-05-13 | 2026-05-13 | 1.00d | 8.75d | ENT 7 Day Working
Secant Piling Operations |  | 2026-05-14 | 2026-06-01 | 19.00d | 8.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7160 | Piling work- 7 soft pile (1 pile/d, pile depth ≈ 30m | 2026-05-14 | 2026-05-20 | 7.00d | 8.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7170 | Piling work- 5 hard pile (1 pile/d, pile depth ≈ 30m | 2026-05-21 | 2026-05-25 | 5.00d | 8.75d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-7180 | Piling work- 7 soft pile (1 pile/d, pile depth ≈ 30m | 2026-05-26 | 2026-06-01 | 7.00d | 8.75d | ENT 7 Day Working
Shaft 2 BroadWater Wood |  | 2026-05-14 | 2026-06-05 | 15.66d | 27.52d
Guide Wall |  | 2026-05-14 | 2026-05-20 | 7.00d | 39.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6890 | Excavate & Blinding - Guide Wall | 2026-05-14 | 2026-05-14 | 1.00d | 39.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6900 | Steel Fixing & Formwork - Guide Wall (internal & External, L=70m) | 2026-05-15 | 2026-05-17 | 3.00d | 39.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6910 | Concrete - Guide wall | 2026-05-18 | 2026-05-18 | 1.00d | 39.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6920 | Curing time | 2026-05-19 | 2026-05-20 | 2.00d | 39.52d | ENT 7 Day Working
Preparation Work for piling Rig |  | 2026-05-22 | 2026-05-30 | 8.33d | 45.85d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6930 | Installation Concrete Infill slab | 2026-05-22 | 2026-05-22 | 1.00d | 39.52d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6940 | Steel cages fabrication | 2026-05-23 | 2026-05-30 | 7.33d | 45.85d | ENT 7 Day Working
AMP8-DD&B-ROS-CON-6950 | Curing time for Infill slab | 2026-05-23 | 2026-05-24 | 2.00d | 39.52d | ENT 7 Day Working
Secant Piling Operations |  | 2026-05-26 | 2026-06-05 | 9.66d | 33.52d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6820 | Piling work- 7 soft pile (1.5 pile/d, pile depth ≈ 22m | 2026-05-26 | 2026-05-30 | 4.66d | 33.52d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-6830 | Piling work- 5 hard pile (1 pile/d, pile depth ≈ 22m | 2026-05-30 | 2026-06-05 | 5.00d | 33.52d | ENT 6 Day Working
AMP8-DD&B-ROS-CON-1780 | Mobilise Equipment To Site (DEPENDENT UPON EARLY ORDER TO SECURE) | 2026-05-22 | 2026-05-25 | 3.00d | 0.50d | ENT 7 Day Working
Drive from S5 to S7, 359m |  | 2026-05-25 | 2026-06-01 | 7.00d | 0.55d | ENT 24 hr Working
Setup TBM |  | 2026-05-25 | 2026-06-01 | 7.00d | 0.55d | ENT 24 hr Working
AMP8-DD&B-ROS-CON-4710 | Survey & Setout TBM Line and Level | 2026-05-25 | 2026-05-26 | 1.00d | 0.55d | ENT 24 hr Working
AMP8-DD&B-ROS-CON-4720 | Install Lunch Rails/ Cradle, Install Jacking Rig | 2026-05-25 | 2026-05-27 | 1.50d | 0.55d | ENT 24 hr Working
AMP8-DD&B-ROS-CON-4730 | Install Thrust frame & Install surface equipments | 2026-05-27 | 2026-05-29 | 2.00d | 0.55d | ENT 24 hr Working
AMP8-DD&B-ROS-CON-4740 | Install Hydraulic jacks & connect system | 2026-05-29 | 2026-05-30 | 1.00d | 0.55d | ENT 24 hr Working
AMP8-DD&B-ROS-CON-4750 | Install Eye Frame & install TBM and commission | 2026-05-30 | 2026-06-01 | 2.50d | 0.55d | ENT 24 hr Working
AMP8-DD&B-ROS-CON-2110 | Earliest Mobilisation Following Completion of Tunnelling Works Out of S2 | 2026-05-01 | 2026-05-01 | 1.00d | 76.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2120 | Mobilise to Work Area | 2026-05-05 | 2026-05-05 | 1.00d | 76.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2130 | Clear area of vegetation and civilise | 2026-05-06 | 2026-05-06 | 1.00d | 76.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2140 | Earthworks to level area off | 2026-05-07 | 2026-05-07 | 1.00d | 76.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2150 | Vacume excavation to perimeter of cofferdam and location of existing GRP main | 2026-05-08 | 2026-05-08 | 1.00d | 76.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2160 | Mobilise Giken Silent Press Rig + Reaction Frame (Temp Works?) | 2026-05-11 | 2026-05-11 | 1.00d | 76.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2170 | Drive Sheets to formation (40m x 6m) | 2026-05-12 | 2026-05-18 | 5.00d | 76.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2180 | Excavate & Frame | 2026-05-19 | 2026-06-02 | 10.00d | 76.00d | ENT 5 Day Working
Downstream Connection (Shaft 7) West Way |  | 13-Mar-26 A | 2026-06-01 | 20.00d | 29.00d | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2510 | Isuue TTRO request | 13-Mar-26 A | 13-Mar-26 A | 0.00d |  | ENT 5 Day Working
AMP8-DD&B-ROS-CON-2520 | TTRO notice period - 12 weeks | 16-Mar-26 A | 2026-06-01 | 20.00d | 29.00d | ENT 5 Day Working