## Sheet1
Arup Design |  | 32.00d | 02-Mar-2026 A | 2026-05-19
Arup Key Dates |  | 5.00d | 02-Mar-2026 A | 2026-05-19
AR-FL-KD-1000 | Contract Start | 0.00d | 02-Mar-2026 A
AR-FL-KD-1010 | Team Mobilisation | 0.00d | 03-Mar-2026 A | 06-Mar-2026 A
AR-FL-KD-1020 | Planned Completion | 0.00d |  | 2026-05-12
AR-FL-KD-1030 | Terminal Float | 5.00d | 2026-05-13 | 2026-05-19
AR-FL-KD-1040 | Completion | 0.00d |  | 2026-05-19
Deliverables |  | 0.00d | 02-Mar-2026 A | 2026-04-01
AR-FL-GET-1000 | Construction Sequence - JMS | 0.00d | 02-Mar-2026 A
AR-FL-GET-1010 | Contractor Preferences on Structure/Material type - JMS | 0.00d | 02-Mar-2026 A
AR-FL-GET-1020 | Max lifting requrements & temp works - JMS | 0.00d | 02-Mar-2026 A
AR-FL-GET-1030 | Tender Design - Design Parameters - JMS | 0.00d | 02-Mar-2026 A
AR-FL-GET-1040 | Tender Design - Full Loading Schedule - JMS | 0.00d | 02-Mar-2026 A
AR-FL-GET-1050 | Ground Investigation Factual Report - JMS | 0.00d | 02-Mar-2026 A
AR-FL-GET-1060 | Surcharge Load Adjacent to Tank - JMS | 0.00d | 02-Mar-2026 A
AR-FL-GET-1070 | Tank Lid Loads - JMS- UU | 0.00d | 2026-04-01
AR-FL-GET-1080 | M&E Loads inside Tanks - JMS - UU | 0.00d | 2026-04-01
Data Review and Initial Analysis |  | 3.00d | 02-Mar-2026 A | 2026-04-07
AR-FL-DRIA-1000 | Receive data from JMS Ltd | 0.00d | 02-Mar-2026 A
AR-FL-DRIA-1010 | Review Data | 0.00d | 09-Mar-2026 A | 13-Mar-2026 A
AR-FL-DRIA-1020 | Site visit window | 0.00d | 09-Mar-2026 A | 13-Mar-2026 A
AR-FL-DRIA-1030 | JMS Confirm construction sequence Validate outline design | 0.00d |  | 16-Mar-2026 A
AR-FL-DRIA-1040 | Validate Outline Design | 0.00d | 16-Mar-2026 A | 25-Mar-2026 A
AR-FL-DRIA-1050 | GI Report & Constructability Review | 0.00d | 19-Mar-2026 A | 25-Mar-2026 A
AR-FL-DRIA-1060 | Deliverable - GI Report & Constructability Review | 3.00d | 26-Mar-2026 A | 2026-04-07
Detailed Design |  | 27.00d | 2026-04-08 | 2026-05-15
Structural Design -Sizing & Loads |  | 15.00d | 2026-04-08 | 2026-04-28
AR-FL-DDST-1000 | Beams & cover slab | 5.00d | 2026-04-08 | 2026-04-14
AR-FL-DDST-1010 | Central Flushing column | 3.00d | 2026-04-15 | 2026-04-17
AR-FL-DDST-1020 | Base Slab | 5.00d | 2026-04-20 | 2026-04-24
AR-FL-DDST-1030 | Design Review | 2.00d | 2026-04-27 | 2026-04-28
Getechnical Design |  | 27.00d | 2026-04-08 | 2026-05-15
AR-FL-DDGD-1000 | General Ground Model | 2.00d | 2026-04-08 | 2026-04-09
AR-FL-DDGD-1010 | Pile Base Connection | 5.00d | 2026-04-20 | 2026-04-24
AR-FL-DDGD-1020 | Pile design | 5.00d | 2026-04-27 | 2026-05-01
AR-FL-DDGD-1030 | Ground movement assessment | 5.00d | 2026-05-05 | 2026-05-11
AR-FL-DDGD-1040 | Generate Specification | 5.00d | 2026-05-11 | 2026-05-15
AR-FL-DDGD-1050 | Confirm Pile | 0.00d | 2026-05-12 | 2026-05-12
AR-FL-DDGD-1060 | Pile GA Drawing | 1.00d | 2026-05-12 | 2026-05-12
AR-FL-DDGD-1070 | Issue Specification & Pile GA | 0.00d |  | 2026-05-15