## TASK
Activity ID | Activity Name | Remaining Duration | Start | Finish | Activity % Complete (%) | BL Project Start | BL Project Finish | Variance - BL Project Finish Date | Total Float | Primary Constraint
DD&B-B&Q-ECI-2100 | Identification of potential advanced works | 8 | 2026-04-10 08:00 | 2026-04-21 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1410 | Review and identify and gaps with planning, permits,consents, stakeholder management plan | 5 | 2026-05-29 08:00 | 2026-06-04 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1390 | Produce Construction phase constraints plan | 15 | 2026-06-05 08:00 | 2026-06-25 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1370 | Submit to UU | 1 | 2026-07-03 08:00 | 2026-07-03 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1360 | Internal governance | 5 | 2026-06-26 08:00 | 2026-07-02 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1350 | Produce CEMP | 15 | 2026-06-05 08:00 | 2026-06-25 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1340 | Produce high risk activites / constraints doc & how they are managed | 10 | 2026-06-05 08:00 | 2026-06-18 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1330 | Finalise Procurement Strategy & Schedule | 5 | 2026-06-12 08:00 | 2026-06-18 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1320 | Produce Temp Works Schedule | 10 | 2026-05-29 08:00 | 2026-06-11 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1310 | Finalise P6 programme | 10 | 2026-06-05 08:00 | 2026-06-18 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1300 | Finalise Procurement Strategy inc recommendations | 5 | 2026-06-05 08:00 | 2026-06-11 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1290 | Finalise methodology following supplier quote / programme review | 5 | 2026-05-21 08:00 | 2026-05-28 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1280 | Seek quotations from supply chain | 15 | 2026-05-07 08:00 | 2026-05-28 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1260 | Formulation of estimate | 35 | 2026-05-07 08:00 | 2026-06-25 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1250 | Explore and agree consenting & 3rd party stakeholder requirements | 5 | 2026-04-29 08:00 | 2026-05-06 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1240 | Pull together sub-contract strategy and preferred suppliers (PEP?) | 5 | 2026-04-29 08:00 | 2026-05-06 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1220 | Generate high level P6 programme for design & build phases | 8 | 2026-04-24 08:00 | 2026-05-06 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1210 | Formulate methodology inc TW via buildability workshops (PEP?) | 5 | 2026-04-22 08:00 | 2026-04-28 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1200 | Generate R&O Register | 35 | 2026-04-22 08:00 | 2026-06-11 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1180 | Agreement of baseline GI data and assumptions in relation to GI scope, GBR Reports and Contaminated Land etc. | 8 | 2026-04-10 08:00 | 2026-04-21 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1170 | Review existing information, site visit etc Inc Review outline design and GI reports and identify any issue | 8 | 2026-04-10 08:00 | 2026-04-21 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1160 | Cost Plan Kick Off Meeting | 1 | 2026-04-09 08:00 | 2026-04-09 17:00 | 0 |  |  |  | 0 | As Late As Possible
DD&B-B&Q-ECI-1150 | Design Freeze | 0 | 2026-04-09 08:00 |  | 0 |  |  |  | 0 | As Late As Possible
AMP8-FPS-UU-2040 | Conservation area consent | 0 |  | 2026-02-13 12:00 | 0 |  | 2026-02-13 12:00 | 0 | 7 | As Late As Possible
AMP8-FPS-UU-1140 | BT overhead diversions | 0 |  | 2026-02-13 12:00 | 0 |  | 2026-02-13 12:00 | 0 | 7 | As Late As Possible
AMP8-FPS-UU-1130 | Land access within the working area | 0 |  | 2026-02-13 12:00 | 0 |  | 2026-02-13 12:00 | 0 | 7 | As Late As Possible
AMP8-FPS-UU-1120 | Tree surveys | 0 |  | 2026-02-13 12:00 | 0 |  | 2026-02-13 12:00 | 0 | 7 | As Late As Possible
AMP8-FPS-UU-1110 | Utility searches | 0 |  | 2026-02-13 12:00 | 0 |  | 2026-02-13 12:00 | 0 | 7 | As Late As Possible
AMP8-FPS-UU-1100 | GPR Surveys | 0 |  | 2026-02-13 12:00 | 0 |  | 2026-02-13 12:00 | 0 | 7 | As Late As Possible
AMP8-FPS-UU-1090 | Topographical surveys | 0 |  | 2026-02-13 12:00 | 0 |  | 2026-02-13 12:00 | 0 | 7 | As Late As Possible
AMP8-FPS-UU-1080 | Ground investigations & report | 0 |  | 2026-02-13 12:00 | 0 |  | 2026-02-13 12:00 | 0 | 7 | As Late As Possible
AMP8-FPS-PROC-3220 | HRA UU Approval | 10 | 2026-01-29 13:00 | 2026-02-12 12:00 | 0 | 2026-01-29 13:00 | 2026-02-12 12:00 | 0 | 7
AMP8-FPS-PROC-3210 | HRA Survey Support - lead | 1 | 2026-01-21 13:00 | 2026-01-22 12:00 | 0 | 2026-01-21 13:00 | 2026-01-22 12:00 | 0 | 7
AMP8-FPS-PROC-3200 | HRA Survey Support - Issue Contract | 1 | 2026-01-21 08:00 | 2026-01-21 12:00 | 0 | 2026-01-21 08:00 | 2026-01-21 12:00 | 0 | 7
AMP8-FPS-PROC-3190 | Secant piling - lead (build) | 35 | 2026-04-17 08:00 | 2026-06-08 17:00 | 0 | 2026-04-17 08:00 | 2026-06-08 17:00 | 0 | 0
AMP8-FPS-PROC-2170 | Third party approvals | 0 |  | 2026-02-13 12:00 | 0 |  | 2026-02-13 12:00 | 0 | 7 | As Late As Possible
AMP8-FPS-PROC-2150 | Surfacing - governance | 70 | 2026-01-21 08:00 | 2026-04-30 17:00 | 0 | 2026-01-21 08:00 | 2026-04-30 17:00 | 0 | 19
AMP8-FPS-PROC-2100 | Hoarding - lead | 15 | 2026-03-04 08:00 | 2026-03-24 17:00 | 0 | 2026-03-04 08:00 | 2026-03-24 17:00 | 0 | 2
AMP8-FPS-PROC-2080 | Deveg / tree removal - lead | 15 | 2026-02-04 08:00 | 2026-02-24 17:00 | 0 | 2026-02-04 08:00 | 2026-02-24 17:00 | 0 | 5
AMP8-FPS-PROC-2060 | Concrete - lead | 20 | 2026-05-11 08:00 | 2026-06-08 17:00 | 0 | 2026-05-11 08:00 | 2026-06-08 17:00 | 0 | 0 | As Late As Possible
AMP8-FPS-PROC-2050 | Aggregates - lead | 10 | 2026-02-05 13:00 | 2026-02-19 12:00 | 0 | 2026-02-05 13:00 | 2026-02-19 12:00 | 0 | 7 | As Late As Possible
AMP8-FPS-PROC-2030 | Footpath closure notices - 3 month period (PROW) | 60 | 2026-01-07 08:00 | 2026-03-31 17:00 | 0 | 2026-01-07 08:00 | 2026-03-31 17:00 | 0 | 17
AMP8-FPS-PROC-2020 | NRSWA permits | 5 | 2026-02-05 13:00 | 2026-02-12 12:00 | 0 | 2026-02-05 13:00 | 2026-02-12 12:00 | 0 | 17
AMP8-FPS-PROC-2010 | HRA (PBA) Produce & Submit Screening Report | 5 | 2026-01-22 13:00 | 2026-01-29 12:00 | 0 | 2026-01-22 13:00 | 2026-01-29 12:00 | 0 | 7
AMP8-FPS-PROC-1970 | Procurement Start | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 2
AMP8-FPS-PROC-1940 | Piling Design Complete | 0 |  | 2026-04-16 17:00 | 0 |  |  |  | 64
AMP8-FPS-PROC-1930 | Concrete - governance | 30 | 2026-03-25 08:00 | 2026-05-08 17:00 | 0 | 2026-03-25 08:00 | 2026-05-08 17:00 | 0 | 0 | As Late As Possible
AMP8-FPS-PROC-1920 | Aggregates - governance | 0 | 2026-02-05 13:00 | 2026-02-05 13:00 | 0 | 2026-02-05 13:00 | 2026-02-05 13:00 | 0 | 7 | As Late As Possible
AMP8-FPS-PROC-1910 | Secant piling - lead (design) | 15 | 2026-03-25 08:00 | 2026-04-16 17:00 | 0 | 2026-03-25 08:00 | 2026-04-16 17:00 | 0 | 0
AMP8-FPS-PROC-1900 | Deveg / tree removal - governance | 10 | 2026-01-21 08:00 | 2026-02-03 17:00 | 0 | 2026-01-21 08:00 | 2026-02-03 17:00 | 0 | 5
AMP8-FPS-PROC-1890 | Hoarding - governance | 30 | 2026-01-21 08:00 | 2026-03-03 17:00 | 0 | 2026-01-21 08:00 | 2026-03-03 17:00 | 0 | 2
AMP8-FPS-PROC-1880 | Surfacing - lead | 25 | 2026-05-01 08:00 | 2026-06-08 17:00 | 0 | 2026-05-01 08:00 | 2026-06-08 17:00 | 0 | 19
AMP8-FPS-MIL-2110 | Design complete | 0 |  | 2026-06-17 17:00 | 0 |  | 2026-06-17 17:00 | 0 | 12
AMP8-FPS-MIL-1190 | Start on site | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 17
AMP8-FPS-MAE-1760 | MAE design complete | 0 |  | 2026-06-17 17:00 | 0 |  | 2026-06-17 17:00 | 0 | 12
AMP8-FPS-MAE-1750 | Project Completion | 0 |  | 2026-06-17 17:00 | 0 |  | 2026-06-17 17:00 | 0 | 12
AMP8-FPS-MAE-1740 | Final Submission | 0 |  | 2026-06-08 17:00 | 0 |  | 2026-06-08 17:00 | 0 | 19
AMP8-FPS-MAE-1730 | Review and update drawings | 11 | 2026-05-22 08:00 | 2026-06-08 17:00 | 0 | 2026-05-22 08:00 | 2026-06-08 17:00 | 0 | 19
AMP8-FPS-MAE-1720 | Client Review of Design Pack | 11 | 2026-05-07 08:00 | 2026-05-21 17:00 | 0 | 2026-05-07 08:00 | 2026-05-21 17:00 | 0 | 19
AMP8-FPS-MAE-1710 | Submission of Outline Design Pack | 0 | 2026-05-07 08:00 | 2026-05-07 08:00 | 0 | 2026-05-07 08:00 | 2026-05-07 08:00 | 0 | 19
AMP8-FPS-MAE-1700 | Material Take Off | 6 | 2026-04-24 08:00 | 2026-05-01 17:00 | 0 | 2026-04-24 08:00 | 2026-05-01 17:00 | 0 | 21
AMP8-FPS-MAE-1690 | Significant Site Hazard Identification Plan (existing site hazards record/drawing) | 6 | 2026-04-24 08:00 | 2026-05-01 17:00 | 0 | 2026-04-24 08:00 | 2026-05-01 17:00 | 0 | 21
AMP8-FPS-MAE-1680 | Routing, design, drawing | 6 | 2026-04-24 08:00 | 2026-05-01 17:00 | 0 | 2026-04-24 08:00 | 2026-05-01 17:00 | 0 | 21
AMP8-FPS-MAE-1670 | Pipework layout plan c/w pipework and manhole schedule | 4 | 2026-04-20 08:00 | 2026-04-23 17:00 | 0 | 2026-04-20 08:00 | 2026-04-23 17:00 | 0 | 21
AMP8-FPS-MAE-1660 | Civils Pipe Design | 6 | 2026-04-14 08:00 | 2026-04-21 17:00 | 0 | 2026-04-14 08:00 | 2026-04-21 17:00 | 0 | 29
AMP8-FPS-MAE-1650 | Pipe entry/exit details | 6 | 2026-04-13 08:00 | 2026-04-20 17:00 | 0 | 2026-04-13 08:00 | 2026-04-20 17:00 | 0 | 30
AMP8-FPS-MAE-1640 | Mechanical GA drawings - Fluidic Mixer | 4 | 2026-04-14 08:00 | 2026-04-17 17:00 | 0 | 2026-04-14 08:00 | 2026-04-17 17:00 | 0 | 21
AMP8-FPS-MAE-1630 | Mechanical GA drawings - Tremie Pipe | 4 | 2026-04-08 08:00 | 2026-04-13 17:00 | 0 | 2026-04-08 08:00 | 2026-04-13 17:00 | 0 | 21
AMP8-FPS-MAE-1620 | Flowmeter Chamber | 6 | 2026-04-02 08:00 | 2026-04-13 17:00 | 0 | 2026-04-02 08:00 | 2026-04-13 17:00 | 0 | 29
AMP8-FPS-MAE-1610 | Mechanical GA drawings - Tank Entry Pipe | 4 | 2026-03-31 08:00 | 2026-04-07 17:00 | 0 | 2026-03-31 08:00 | 2026-04-07 17:00 | 0 | 21
AMP8-FPS-MAE-1600 | Plan and longitudinal sections – rising main from new to old tank | 11 | 2026-03-25 08:00 | 2026-04-10 17:00 | 0 | 2026-03-25 08:00 | 2026-04-10 17:00 | 0 | 30
AMP8-FPS-MAE-1590 | Mechanical GA drawings - Pumps in Shaft GA and Risers | 4 | 2026-03-25 08:00 | 2026-03-30 17:00 | 0 | 2026-03-25 08:00 | 2026-03-30 17:00 | 0 | 21
AMP8-FPS-MAE-1580 | Valve Chamber | 6 | 2026-03-25 08:00 | 2026-04-01 17:00 | 0 | 2026-03-25 08:00 | 2026-04-01 17:00 | 0 | 29
AMP8-FPS-MAE-1570 | Tank kiosk enclosure foundation | 6 | 2026-04-28 08:00 | 2026-05-06 17:00 | 0 | 2026-04-28 08:00 | 2026-05-06 17:00 | 0 | 19
AMP8-FPS-MAE-1560 | DNO/MCC Main Incomer Kiosk Location Plan | 6 | 2026-04-20 08:00 | 2026-04-27 17:00 | 0 | 2026-04-20 08:00 | 2026-04-27 17:00 | 0 | 19
AMP8-FPS-MAE-1550 | Lightning Protection Risk Assessment | 11 | 2026-04-20 08:00 | 2026-05-05 17:00 | 0 | 2026-04-20 08:00 | 2026-05-05 17:00 | 0 | 20
AMP8-FPS-MAE-1540 | HAZOP and ALM Report - SST & DD&B | 6 | 2026-04-20 08:00 | 2026-04-27 17:00 | 0 | 2026-04-20 08:00 | 2026-04-27 17:00 | 0 | 25
AMP8-FPS-MAE-1510 | Block Cable Diagram | 6 | 2026-04-01 08:00 | 2026-04-10 17:00 | 0 | 2026-04-01 08:00 | 2026-04-10 17:00 | 0 | 24
AMP8-FPS-MAE-1500 | Power Supply Assessment – provide data for power application by UU (DNO APPLICATION BY UU) | 11 | 2026-04-01 08:00 | 2026-04-17 17:00 | 0 | 2026-04-01 08:00 | 2026-04-17 17:00 | 0 | 19
AMP8-FPS-MAE-1490 | HAZOP and ALM action close out | 11 | 2026-04-01 08:00 | 2026-04-17 17:00 | 0 | 2026-04-01 08:00 | 2026-04-17 17:00 | 0 | 25
AMP8-FPS-MAE-1480 | HAZOP and ALM workshop record | 3 | 2026-03-27 08:00 | 2026-03-31 17:00 | 0 | 2026-03-27 08:00 | 2026-03-31 17:00 | 0 | 25
AMP8-FPS-MAE-1470 | Lifting Register | 6 | 2026-03-26 08:00 | 2026-04-02 17:00 | 0 | 2026-03-26 08:00 | 2026-04-02 17:00 | 0 | 34
AMP8-FPS-MAE-1460 | Mechanical equipment schedule | 6 | 2026-03-26 08:00 | 2026-04-02 17:00 | 0 | 2026-03-26 08:00 | 2026-04-02 17:00 | 0 | 34
AMP8-FPS-MAE-1450 | HAZOP and ALM workshop | 2 | 2026-03-25 08:00 | 2026-03-26 17:00 | 0 | 2026-03-25 08:00 | 2026-03-26 17:00 | 0 | 25
AMP8-FPS-MAE-1430 | Single Line Diagram | 6 | 2026-03-24 08:00 | 2026-03-31 17:00 | 0 | 2026-03-24 08:00 | 2026-03-31 17:00 | 0 | 24
AMP8-FPS-MAE-1420 | Power Assessments (From SST Deliverables) | 6 | 2026-03-24 08:00 | 2026-03-31 17:00 | 0 | 2026-03-24 08:00 | 2026-03-31 17:00 | 0 | 19
AMP8-FPS-MAE-1410 | Telemetry schedules (in prescribed format per UU spreadsheet) | 4 | 2026-03-18 08:00 | 2026-03-23 17:00 | 0 | 2026-03-18 08:00 | 2026-03-23 17:00 | 0 | 30
AMP8-FPS-MAE-1400 | Outline Design - Load Schedule | 4 | 2026-03-18 08:00 | 2026-03-23 17:00 | 0 | 2026-03-18 08:00 | 2026-03-23 17:00 | 0 | 19
AMP8-FPS-MAE-1390 | Pump system curve, complete with selected/purchased pump curve | 6 | 2026-03-18 08:00 | 2026-03-25 17:00 | 0 | 2026-03-18 08:00 | 2026-03-25 17:00 | 0 | 34
AMP8-FPS-MAE-1380 | Network Architecture Drawing | 6 | 2026-03-10 08:00 | 2026-03-17 17:00 | 0 | 2026-03-10 08:00 | 2026-03-17 17:00 | 0 | 30
AMP8-FPS-MAE-1370 | Obtain Pump Selection | 6 | 2026-03-10 08:00 | 2026-03-17 17:00 | 0 | 2026-03-10 08:00 | 2026-03-17 17:00 | 0 | 19
AMP8-FPS-MAE-1360 | HAZOP and ALM Workshop document pack inc Fire Safety Review record Submission | 6 | 2026-03-10 08:00 | 2026-03-17 17:00 | 0 | 2026-03-10 08:00 | 2026-03-17 17:00 | 0 | 25
AMP8-FPS-MAE-1350 | Pump Datasheet | 6 | 2026-03-02 08:00 | 2026-03-09 17:00 | 0 | 2026-03-02 08:00 | 2026-03-09 17:00 | 0 | 19
AMP8-FPS-MAE-1320 | User Requirement Specification | 11 | 2026-02-23 08:00 | 2026-03-09 17:00 | 0 | 2026-02-23 08:00 | 2026-03-09 17:00 | 0 | 25
AMP8-FPS-MAE-1310 | Shaft design inc. benching, cover slab, pipe entry/exit | 22 | 2026-02-23 08:00 | 2026-03-24 17:00 | 0 | 2026-02-23 08:00 | 2026-03-24 17:00 | 0 | 0
AMP8-FPS-MAE-1300 | 1050mm overflow design | 10 | 2026-02-23 08:00 | 2026-03-06 17:00 | 0 | 2026-02-23 08:00 | 2026-03-06 17:00 | 0 | 59
AMP8-FPS-MAE-1290 | Dangerous Substances and Explosive Atmospheres Regulations (DSEAR) Assessment | 11 | 2026-02-13 08:00 | 2026-02-27 17:00 | 0 | 2026-02-13 08:00 | 2026-02-27 17:00 | 0 | 19
AMP8-FPS-MAE-1280 | Hydraulic Calculations - Emptying - pipe sizing and pump head loss calc | 11 | 2026-02-13 08:00 | 2026-02-27 17:00 | 0 | 2026-02-13 08:00 | 2026-02-27 17:00 | 0 | 19
AMP8-FPS-MAE-1270 | Control Philosophy | 6 | 2026-02-13 08:00 | 2026-02-20 17:00 | 0 | 2026-02-13 08:00 | 2026-02-20 17:00 | 0 | 25
AMP8-FPS-MAE-1260 | Assessment of structure | 6 | 2026-01-21 08:00 | 2026-01-28 17:00 | 0 | 2026-01-21 08:00 | 2026-01-28 17:00 | 0 | 54
AMP8-FPS-MAE-1250 | Digital time | 4 | 2026-01-21 08:00 | 2026-01-26 17:00 | 0 | 2026-01-21 08:00 | 2026-01-26 17:00 | 0 | 56
AMP8-FPS-MAE-1230 | Outline P&IDs (required for HAZOP) (Piping & Instrument Diagrams) | 6 | 2026-02-05 08:00 | 2026-02-12 17:00 | 0 | 2026-02-05 08:00 | 2026-02-12 17:00 | 0 | 49
AMP8-FPS-MAE-1220 | GDR | 6 | 2026-02-06 08:00 | 2026-02-13 17:00 | 0 | 2026-02-06 08:00 | 2026-02-13 17:00 | 0 | 5
AMP8-FPS-MAE-1210 | JMS Response to TQs | 11 | 2026-02-06 08:00 | 2026-02-20 17:00 | 0 | 2026-02-06 08:00 | 2026-02-20 17:00 | 0 | 0
AMP8-FPS-MAE-1180 | Basis of Design | 11 | 2026-01-29 08:00 | 2026-02-12 17:00 | 0 | 2026-01-29 08:00 | 2026-02-12 17:00 | 0 | 11
AMP8-FPS-MAE-1170 | Review available GI for shaft design | 6 | 2026-01-29 08:00 | 2026-02-05 17:00 | 0 | 2026-01-29 08:00 | 2026-02-05 17:00 | 0 | 5
AMP8-FPS-MAE-1150 | Scope Surveys for scanning of exisiting assets | 6 | 2026-01-29 08:00 | 2026-02-05 17:00 | 0 | 2026-01-29 08:00 | 2026-02-05 17:00 | 0 | 54
AMP8-FPS-MAE-1130 | Review Information and raise RFIs/TQs | 6 | 2026-01-29 08:00 | 2026-02-05 17:00 | 0 | 2026-01-29 08:00 | 2026-02-05 17:00 | 0 | 0
AMP8-FPS-MAE-1120 | Mobilisation | 6 | 2026-01-21 08:00 | 2026-01-28 17:00 | 0 | 2026-01-21 08:00 | 2026-01-28 17:00 | 0 | 0
AMP8-FPS-MAE-1110 | MAE Project Start | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 0
AMP8-FPS-MAE-1100 | Catchment Area EPD (Explosion Protection Document)- Confirmation of Hazardous Substances in existing tank | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 11
AMP8-FPS-MAE-1090 | Confirmation of detention tank type | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 11
AMP8-FPS-MAE-1080 | Feasibility Control Philosophy | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 17
AMP8-FPS-MAE-1070 | All existing drawings in dwg format | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 11
AMP8-FPS-MAE-1060 | Flowrate from existing shaft | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 17
AMP8-FPS-MAE-1050 | Historical model? | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 11
AMP8-FPS-MAE-1040 | GFR | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 17
AMP8-FPS-MAE-1020 | Historical as-built drawings | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 11
AMP8-FPS-MAE-1010 | Topographical data and drawing from UU | 0 | 2026-01-21 08:00 |  | 0 | 2026-01-21 08:00 |  | 0 | 11
AMP8-FPS-MAE-1000 | MAE contract award | 0 |  | 2026-01-20 17:00 | 0 |  | 2026-01-20 17:00 | 0 | 0
AMP8-FPS-KD-2130 | Terminal float @10% | 10 | 2026-07-06 08:00 | 2026-07-17 17:00 | 0 | 2026-07-06 08:00 | 2026-07-17 17:00 | 0 | 0
AMP8-FPS-KD-2120 | Contract Completion CC 19th July | 0 |  | 2026-07-20 08:00 | 0 |  | 2026-07-20 08:00 | 0 | 0 | Mandatory Finish
AMP8-FPS-KD-2110 | Planned completion | 0 |  | 2026-07-03 17:00 | 0 |  | 2026-07-03 17:00 | 0 | 0
AMP8-FPS-KD-2100 | Start date lead in (Mobilisation) | 0 | 2026-01-07 08:00 |  | 0 | 2026-01-07 08:00 |  | 0 | 0 | Start On or After
AMP8-FPS-KD-2040 | Start date lead in (Mobilisation) | 10 | 2026-01-07 08:00 | 2026-01-20 17:00 | 0 | 2026-01-07 08:00 | 2026-01-20 17:00 | 0 | 0
AMP8-FPS-KD-1440 | ECI Contract award | 0 | 2025-12-15 08:00 |  | 0 | 2025-12-15 08:00 |  | 0 | 0 | Start On
AMP8-FPS-EAW-2020 | Further subsoil excavation to piling matt | 4 | 2026-05-12 08:00 | 2026-05-15 17:00 | 0 | 2026-05-12 08:00 | 2026-05-15 17:00 | 0 | 1
AMP8-FPS-EAW-1430 | Import aggregates for initial compound area (1411 t) 70 wagons | 5 | 2026-04-08 08:00 | 2026-04-14 17:00 | 0 | 2026-04-08 08:00 | 2026-04-14 17:00 | 0 | 5
AMP8-FPS-EAW-1420 | Soil strip for initial compound area (882m3) (Store Onsite ??) | 3 | 2026-04-01 08:00 | 2026-04-07 17:00 | 0 | 2026-04-01 08:00 | 2026-04-07 17:00 | 0 | 5
AMP8-FPS-EAW-1330 | RC platform Infill | 2 | 2026-07-02 08:00 | 2026-07-03 17:00 | 0 | 2026-07-02 08:00 | 2026-07-03 17:00 | 0 | 0
AMP8-FPS-EAW-1320 | Submit streetlight and electrical cable removal request to LA | 6 | 2026-01-21 08:00 | 2026-01-28 17:00 | 0 | 2026-01-21 08:00 | 2026-01-28 17:00 | 0 | 1
AMP8-FPS-EAW-1310 | Backfill and compact with type 1 | 3 | 2026-05-18 08:00 | 2026-05-20 17:00 | 0 | 2026-05-18 08:00 | 2026-05-20 17:00 | 0 | 1
AMP8-FPS-EAW-1300 | Streetlight and electrical cable removal (assumption) | 10 | 2026-04-13 08:00 | 2026-04-24 17:00 | 0 | 2026-04-13 08:00 | 2026-04-24 17:00 | 0 | 1
AMP8-FPS-EAW-1290 | Pre-dig shaft footprint | 20 | 2026-03-25 08:00 | 2026-04-23 17:00 | 0 | 2026-03-25 08:00 | 2026-04-23 17:00 | 0 | 2
AMP8-FPS-EAW-1280 | Site wide vegetation/tree clearance | 6 | 2026-02-25 08:00 | 2026-03-04 17:00 | 0 | 2026-02-25 08:00 | 2026-03-04 17:00 | 0 | 5
AMP8-FPS-EAW-1270 | LA - Streetlight and electrical cable removal review period | 50 | 2026-01-29 08:00 | 2026-04-10 17:00 | 0 | 2026-01-29 08:00 | 2026-04-10 17:00 | 0 | 1
AMP8-FPS-EAW-1260 | Guide wall construction | 14 | 2026-06-09 08:00 | 2026-06-26 17:00 | 0 | 2026-06-09 08:00 | 2026-06-26 17:00 | 0 | 0
AMP8-FPS-EAW-1250 | Backfill and regrade around guide wall | 3 | 2026-06-29 08:00 | 2026-07-01 17:00 | 0 | 2026-06-29 08:00 | 2026-07-01 17:00 | 0 | 0
AMP8-FPS-EAW-1240 | Excavate and Import aggregates to create working platform and access for pre-dig | 11 | 2026-05-21 08:00 | 2026-06-05 17:00 | 0 | 2026-05-21 08:00 | 2026-06-05 17:00 | 0 | 1
AMP8-FPS-EAW-1230 | Compound drainage (Meterage) | 4 | 2026-04-15 08:00 | 2026-04-20 17:00 | 0 | 2026-04-15 08:00 | 2026-04-20 17:00 | 0 | 5
AMP8-FPS-EAW-1220 | Site hoarding / segregation at pub car park and site access | 5 | 2026-03-25 08:00 | 2026-03-31 17:00 | 0 | 2026-03-25 08:00 | 2026-03-31 17:00 | 0 | 5
AMP8-FPS-EAW-1210 | Topsoil strip and stockpile remaining working area and compound | 10 | 2026-04-27 08:00 | 2026-05-11 17:00 | 0 | 2026-04-27 08:00 | 2026-05-11 17:00 | 0 | 1
AMP8-FPS-EAW-1200 | Site hoarding to working area (Linear Meterage) | 20 | 2026-03-25 08:00 | 2026-04-23 17:00 | 0 | 2026-03-25 08:00 | 2026-04-23 17:00 | 0 | 2
AMP8-FPS-EAW-1180 | Water supply installation | 5 | 2026-03-25 08:00 | 2026-03-31 17:00 | 0 | 2026-03-25 08:00 | 2026-03-31 17:00 | 0 | 5
AMP8-FPS-EAW-1170 | Widen access to pub car park inc. surfacing | 3 | 2026-03-13 08:00 | 2026-03-17 17:00 | 0 | 2026-03-13 08:00 | 2026-03-17 17:00 | 0 | 5
AMP8-FPS-EAW-1160 | Install temporary compound | 4 | 2026-02-19 13:00 | 2026-02-25 12:00 | 0 | 2026-02-19 13:00 | 2026-02-25 12:00 | 0 | 7
AMP8-FPS-EAW-1150 | Mobilisation | 2 | 2026-02-13 13:00 | 2026-02-17 12:00 | 0 | 2026-02-13 13:00 | 2026-02-17 12:00 | 0 | 7
AMP8-FPS-EAW-1140 | Install additional parking for bowls club | 5 | 2026-03-18 08:00 | 2026-03-24 17:00 | 0 | 2026-03-18 08:00 | 2026-03-24 17:00 | 0 | 5
AMP8-FPS-EAW-1130 | Widen access to existing road inc. surfacing | 6 | 2026-03-05 08:00 | 2026-03-12 17:00 | 0 | 2026-03-05 08:00 | 2026-03-12 17:00 | 0 | 5
AMP8-FPS-EAW-1120 | Set up temporary fencing | 2 | 2026-02-17 13:00 | 2026-02-19 12:00 | 0 | 2026-02-17 13:00 | 2026-02-19 12:00 | 0 | 7
AMP8-FPS-DED-3870 | Design Approved | 6 | 2026-05-26 08:00 | 2026-06-02 17:00 | 0 | 2026-05-26 08:00 | 2026-06-02 17:00 | 0 | 21
AMP8-FPS-DED-3860 | Incorporate Comments | 6 | 2026-05-15 08:00 | 2026-05-22 17:00 | 0 | 2026-05-15 08:00 | 2026-05-22 17:00 | 0 | 21
AMP8-FPS-DED-3850 | Client Design Review / Approval | 10 | 2026-04-30 08:00 | 2026-05-14 17:00 | 0 | 2026-04-30 08:00 | 2026-05-14 17:00 | 0 | 12
AMP8-FPS-DED-3820 | Contract negotiation | 20 | 2025-12-15 08:00 | 2026-01-27 17:00 | 0 | 2025-12-15 08:00 | 2026-01-27 17:00 | 0 | 12
AMP8-FPS-DED-3730 | Kiosk | 28 | 2026-04-30 08:00 | 2026-06-10 17:00 | 0 | 2026-04-30 08:00 | 2026-06-10 17:00 | 0 | 12
AMP8-FPS-DED-3580 | MTS design complete | 0 |  | 2026-06-02 17:00 | 0 |  | 2026-06-02 17:00 | 0 | 23
AMP8-FPS-DED-3450 | MTS design mobilisation | 6 | 2026-01-28 08:00 | 2026-02-04 17:00 | 0 | 2026-01-28 08:00 | 2026-02-04 17:00 | 0 | 12
AMP8-FPS-DED-3440 | MTS contract award | 0 |  | 2026-01-27 17:00 | 0 |  | 2026-01-27 17:00 | 0 | 12
AMP8-FPS-DED-32080 | Produce O&M template/manual | 2 | 2026-06-03 08:00 | 2026-06-04 17:00 | 0 | 2026-06-03 08:00 | 2026-06-04 17:00 | 0 | 21
AMP8-FPS-DED-3200 | Instrumentation package review & approval | 5 | 2026-06-11 08:00 | 2026-06-17 17:00 | 0 | 2026-06-11 08:00 | 2026-06-17 17:00 | 0 | 12
AMP8-FPS-DED-3150 | MEICA detailed design | 17 | 2026-03-26 08:00 | 2026-04-21 17:00 | 0 | 2026-03-26 08:00 | 2026-04-21 17:00 | 0 | 12
AMP8-FPS-DED-3140 | MEICA outline design | 30 | 2026-02-05 08:00 | 2026-03-18 17:00 | 0 | 2026-02-05 08:00 | 2026-03-18 17:00 | 0 | 12
AMP8-FPS-DED-3120 | MEICA design submission/approval | 6 | 2026-04-22 08:00 | 2026-04-29 17:00 | 0 | 2026-04-22 08:00 | 2026-04-29 17:00 | 0 | 12
AMP8-FPS-DED-2790 | Civil's package review & approval | 5 | 2026-03-17 08:00 | 2026-03-23 17:00 | 0 | 2026-03-17 08:00 | 2026-03-23 17:00 | 0 | 33
AMP8-FPS-DED-2780 | GDR | 22 | 2026-01-21 08:00 | 2026-02-19 17:00 | 0 | 2026-01-21 08:00 | 2026-02-19 17:00 | 0 | 75
AMP8-FPS-DED-2770 | IFC | 11 | 2026-04-10 08:00 | 2026-04-24 17:00 | 0 | 2026-04-10 08:00 | 2026-04-24 17:00 | 0 | 48
AMP8-FPS-DED-2760 | New vehicle turning head | 11 | 2026-01-21 08:00 | 2026-02-04 17:00 | 0 | 2026-01-21 08:00 | 2026-02-04 17:00 | 0 | 65
AMP8-FPS-DED-2750 | Existing Ferry PS shaft | 22 | 2026-01-21 08:00 | 2026-02-19 17:00 | 0 | 2026-01-21 08:00 | 2026-02-19 17:00 | 0 | 33
AMP8-FPS-DED-2740 | Storm tank air vent | 10 | 2026-04-27 08:00 | 2026-05-11 17:00 | 0 | 2026-04-27 08:00 | 2026-05-11 17:00 | 0 | 33
AMP8-FPS-DED-2720 | Ducting | 28 | 2026-04-30 08:00 | 2026-06-10 17:00 | 0 | 2026-04-30 08:00 | 2026-06-10 17:00 | 0 | 12
AMP8-FPS-DED-2690 | Davit Arm | 6 | 2026-03-24 08:00 | 2026-03-31 17:00 | 0 | 2026-03-24 08:00 | 2026-03-31 17:00 | 0 | 48
AMP8-FPS-DED-2680 | Geotechnical assessment (tank) | 6 | 2026-03-05 08:00 | 2026-03-12 17:00 | 0 | 2026-03-05 08:00 | 2026-03-12 17:00 | 0 | 66
AMP8-FPS-DED-2670 | 1050mm combined sewer overflow | 17 | 2026-02-20 08:00 | 2026-03-16 17:00 | 0 | 2026-02-20 08:00 | 2026-03-16 17:00 | 0 | 33
AMP8-FPS-DED-2350 | Temporary works designs | 44 | 2026-01-21 08:00 | 2026-03-23 17:00 | 0 | 2026-01-21 08:00 | 2026-03-23 17:00 | 0 | 33
AMP8-FPS-DED-2190 | New vehicle turning head package review & approval | 5 | 2026-02-05 08:00 | 2026-02-11 17:00 | 0 | 2026-02-05 08:00 | 2026-02-11 17:00 | 0 | 65
AMP8-FPS-DED-2180 | Air vent package review & approval | 5 | 2026-05-12 08:00 | 2026-05-18 17:00 | 0 | 2026-05-12 08:00 | 2026-05-18 17:00 | 0 | 33
AMP8-FPS-DED-21710 | Pipework | 11 | 2026-03-24 08:00 | 2026-04-09 17:00 | 0 | 2026-03-24 08:00 | 2026-04-09 17:00 | 0 | 44
AMP8-FPS-DED-21700 | Valve chamber | 22 | 2026-03-24 08:00 | 2026-04-24 17:00 | 0 | 2026-03-24 08:00 | 2026-04-24 17:00 | 0 | 33
AMP8-FPS-DED-2170 | Rising main package review & approval | 5 | 2026-04-27 08:00 | 2026-05-01 17:00 | 0 | 2026-04-27 08:00 | 2026-05-01 17:00 | 0 | 43
AMP8-FPS-DED-2160 | Davit arm package review & approval | 5 | 2026-04-01 08:00 | 2026-04-09 17:00 | 0 | 2026-04-01 08:00 | 2026-04-09 17:00 | 0 | 48
AMP8-FPS-DED-2140 | Secant piling design approval | 5 | 2026-03-05 08:00 | 2026-03-11 17:00 | 0 | 2026-03-05 08:00 | 2026-03-11 17:00 | 0 | 9
AMP8-FPS-DED-2130 | Secant piling design | 30 | 2026-01-22 08:00 | 2026-03-04 17:00 | 0 | 2026-01-22 08:00 | 2026-03-04 17:00 | 0 | 9 | As Late As Possible
AMP8-FPS-DED-2060 | DSEAR submission | 0 |  | 2026-03-18 17:00 | 0 |  | 2026-03-18 17:00 | 0 | 68
AMP8-FPS-DED-2050 | ALM | 0 |  | 2026-03-18 17:00 | 0 |  | 2026-03-18 17:00 | 0 | 12
AMP8-FPS-DED-2040 | HAZOP | 0 |  | 2026-03-18 17:00 | 0 |  | 2026-03-18 17:00 | 0 | 12
AMP8-FPS-DED-2030 | HAZCON actions close out | 5 | 2026-02-13 08:00 | 2026-02-19 17:00 | 0 | 2026-02-13 08:00 | 2026-02-19 17:00 | 0 | 11
AMP8-FPS-DED-2020 | HAZCOMM actions close out | 5 | 2026-02-05 08:00 | 2026-02-11 17:00 | 0 | 2026-02-05 08:00 | 2026-02-11 17:00 | 0 | 98
AMP8-FPS-DED-1930 | DSEAR actions close out | 5 | 2026-03-19 08:00 | 2026-03-25 17:00 | 0 | 2026-03-19 08:00 | 2026-03-25 17:00 | 0 | 68
AMP8-FPS-DED-1920 | HAZCON | 0 |  | 2026-02-12 17:00 | 0 |  | 2026-02-12 17:00 | 0 | 11
AMP8-FPS-DED-1910 | HAZCOMM | 0 |  | 2026-02-04 17:00 | 0 |  | 2026-02-04 17:00 | 0 | 17
AMP8-FPS-DED-1900 | ALM actions close out | 5 | 2026-03-19 08:00 | 2026-03-25 17:00 | 0 | 2026-03-19 08:00 | 2026-03-25 17:00 | 0 | 12
AMP8-FPS-DED-1890 | HAZOP actions close out | 5 | 2026-03-19 08:00 | 2026-03-25 17:00 | 0 | 2026-03-19 08:00 | 2026-03-25 17:00 | 0 | 12
AMP8-FPS-CIV-4510 | White lining / road markings to pub car park | 1 | 2026-03-02 13:00 | 2026-03-03 12:00 | 0 | 2026-03-02 13:00 | 2026-03-03 12:00 | 0 | 7
AMP8-FPS-CIV-4430 | Reinstate old pub car park entrance & relocate benches | 2 | 2026-02-26 13:00 | 2026-03-02 12:00 | 0 | 2026-02-26 13:00 | 2026-03-02 12:00 | 0 | 7
AMP8-FPS-CIV-4260 | Bollard removal | 1 | 2026-02-25 13:00 | 2026-02-26 12:00 | 0 | 2026-02-25 13:00 | 2026-02-26 12:00 | 0 | 7

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Hour ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=dd/mm/yyyy CurrencyFormat=Dollar